## PublicDataReport
Collection Period | Department/ Agency Name | Agency Short Name | Project ID | Project Title | Government Domain | ICT Project Category | Description | Stage | Benefit Category ( Benefit Type) | Date of Closure/ Postponement | PM Methodologies | Initiation Start Date | Planned Initiation End Date | Revised Initiation End Date | Business Case Approval Date | Planned Initiation Cost | Revised initiation Cost | Planned Delivery Start Date | Revised Delivery Start Date | Planned Delivery End Date | Revised Delivery End Date | Planned Delivery Cost | Revised Delivery Cost | Q4 23-24 | Q1 24-25 | Q2 24-25 | Q3 24-25 | Q4 24-25 (Current) | Reporting Comments
Q4 24-25 | Country Fire Authority | CFA | 2151 | CFA Mobile Data Capability and Short Status Messaging (SSM) | Emergencies and Safety | Communication | Development and deployment of the Mobility Data Capability (MDC) platform, incorporating Short Status Messaging, will deliver operational efficiency and safety benefits to members and the community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2010-10-01 | 2012-07-01 | 2020-06-30 | 2020-07-01 | 0 | 45000 | 2020-07-01 |  | 2021-06-30 | 2027-06-30 | 2850000 |  | Amber | Amber | Amber | Amber | Amber | The project is continuing to experience system integration issues for the Short Status Messaging component, resulting in an amber status. Due to this, the delivery of this component will be delayed and included in the broader technology upgrade across the emergency sector.
Q4 24-25 | Court Services Victoria | CSV | 2452 | Courts Case Management System | Law and Justice | Tracking and Workflow | The CMS Project aims to procure and implement a new case management system for Magistrates’ Court and Children’s Court. The system will enable better information sharing between courts and other agencies, and provide better access to case information | Delivery | Efficiency/Productivity (Non Financial) |  | Project Management Excellence (PME) | 2016-07-01 | 2017-05-02 |  | 2017-05-02 | 0 |  | 2017-07-01 |  | 2022-06-30 | 2026-06-30 | 89200000 | 135456000 | Red | Red | Red | Red | Red | Build of Criminal release was materially finalised this quarter with deployment activities to follow. The delay is due to: - data migration (over 740 million records) from multiple legacy systems across both Children's Court of Victoria (ChCV) and Magistrates' Court of Victoria (MCV) - intricacy of in-bound and out-bound interfaces (23 in total) with multiple agencies - scale of testing with the Criminal release larger than Civil and Child Protection combined - delivery of the Family Violence (IVO) release following the Criminal build
Q4 24-25 | V/Line Corporation | V/Line | 2490 | Workforce management | Transport and Vehicles | Human Capital / Workforce Management | The Workforce management project will streamline the workforce management function and deliver an electronic rostering system that support V/Line to ensure it is able to meet daily staffing challenges to provide punctual and reliable train services | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-01-18 | 2018-02-28 | 2023-04-28 | 2023-05-01 | 250000 | 690251 | 2023-05-31 |  | 2026-07-31 | 2026-12-31 | 9680463 |  | Green | Green | Green | Green | Green | The overall health of the Project is on-track.
Q4 24-25 | South West Alliance of Rural Health | SWARH | 2597 | Barwon Health Rostering Project | Health | Management of Process ,Human Capital / Workforce Management ,Human Resources | This project will deliver a Rostering and Time & Attendance system to automate staff rostering processes, improving workforce utilisation, accuracy of resource allocation and delivery of patient care. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2017-07-19 | 2018-05-31 |  | 2018-06-08 | 110640 |  | 2018-07-11 |  | 2019-12-31 | 2025-06-30 | 3443281 | 3883649 | Amber | Amber | Amber | Amber | Red | The rollout to the remainder of the workforce is underway. 3000 employees are now using the platform.
Q4 24-25 | Department of Education | DE | 2690 | Asset Information Management Systems (AIMS) | Education | Content Management,Data Management,Assets/Materials Management | This will deliver a new Asset Information Management System to manage school land & building assets enabling evidence-based decision making at both DE Corporate & School level & support attestation against Asset Management Accountability Framework. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2017-08-01 | 2019-07-31 | 2019-09-30 | 2019-09-30 | 2963222 | 2562342 | 2019-10-01 |  | 2022-09-30 | 2025-07-31 | 12956778 | 25565174 | Amber | Amber | Green | Green | Green | The project is on track to completion; project closure is subject to project control board endorsement and completion of project closure activities. The project is anticipated to close in Q1FY26.
Q4 24-25 | Yarra Valley Water | YV Water | 2822 | Network Communications and IoT Device Management | Environment and Water | Assets/Materials Management | Uplift on existing IT systems to enable rollout of digital water meters, installations of new mechanical meters, and replacement of faulty water meters (both digital and mechanical) that have been commissioned. | Closed - Completed | Cost Reduction (Financial) | 2025-04-29 | PRINCE2 | 2019-05-01 | 2020-01-31 | 2020-10-14 | 2020-10-14 | 350000 | 1300000 | 2020-10-19 |  | 2022-06-30 | 2025-04-29 | 3715000 | 5197799 | Green | Green | Green | Green | Green | Project completed, minor resolutions and enhancements completed and transition into production
Q4 24-25 | South East Water | SE Water | 2823 | Digital Utility Core Capability | Environment and Water | Customer Relationship Management,Data Management,Development and Integration ,Reporting | Delivery of end-to-end business processes across meter management, billing and alerts & alarms, enabling customer data linkage for meter monitoring, and improving efficiency in water usage monitoring and leakage detection | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2025-04-30 | Agile | 2019-06-10 | 2019-06-20 |  | 2019-06-21 | 25000 |  | 2019-06-24 |  | 2020-02-28 | 2025-04-30 | 5123000 | 23100000 | Green | Green | Green | Green | Green | Following the major release of new functionality to support the Digital Meter roll-out for new connections in March, the project concluded and was closed off in Q4. This represents the delivery of the core capability within IT systems required to support the planned digital meter rollout.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 2851 | Digital Radio Upgrade Program - Stage 2 | Emergencies and Safety | Communication | This Program will transition Ambulance Victoria's (AV) regional comms off analogue radio system onto the State’s shared digital network and replace AV's regional radio fleet to provide secure comms and improve community safety and health outcomes. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2019-07-01 | 2019-07-02 |  | 2019-07-02 | 0 |  | 2019-07-03 |  | 2023-06-30 | 2026-06-30 | 70378000 | 117867000 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 2978 | Road Safety Package | Law and Justice | Assets/Materials Management | The Road Safety Package includes a number of initiatives. The initiatives with ICT deliverables are: • Computerised Maintenance Management System (CMMS) • Network Security - Improvements to security of the Fixed Digital Road Safety Camera network. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2019-06-30 | 2020-09-30 | 2021-05-23 | 2021-05-23 | 2787000 | 869178 | 2021-05-24 |  | 2022-04-21 | 2025-07-23 | 6967000 | 13618249 | Green | Green | Green | Green | Green | The Computerised Maintenance Management System (CMMS) initiative was completed in December 2023. This initiative is now closed and CMMS is an operational platform within DJCS. The final milestones for the Network Security initiative were delivered by 30 June 2025, with the entire Fixed Digital Road Safety Camera (FDRSC) network migrated to a centralised firewall protected environment. The project has transitioned to business as usual, in line with the schedule and will formally close after the endorsement of the project closure report in July 2025.
Q4 24-25 | South West Alliance of Rural Health | SWARH | 3003 | Barwon Health Community Electronic Medical Record | Health | Content Management,Data Management,Forms Management,Management of Process ,Security Management ,Systems Management,Tracking and Workflow | Implementation of an Electronic Health Record (EHR) solution for community nursing and community mental health to replace legacy systems | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PMBoK | 2018-03-01 | 2020-10-01 | 2022-04-07 | 2022-04-07 | 0 | 0 | 2022-04-11 |  | 2023-08-28 | 2026-02-28 | 6074206 | 9146120 | Red | Red | Amber | Red | Red | Scheduling and Hospital in the Home functionality is progressing well, with delivery expected in first quarter 2026. The project is anticipated to return to GREEN in the next reporting period following a scheduled review
Q4 24-25 | Fire Rescue Victoria | FRV | 3029 | Fire Rescue Portal | Emergencies and Safety | Systems Management | Design and implement an enterprise Fire and Rescue Services Portal. | Postponed | Compliance (Non Financial) | 2024-03-31 | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-16 |  | 2020-12-16 | 0 |  | 2020-12-17 |  | 2022-04-30 | 2025-06-30 | 2109000 |  | Amber | Amber | Amber | Amber | Red | The Fire Rescue Portal project remains on hold, with formal closure yet to be confirmed by the project sponsor. While no further work is currently underway, future direction will be determined through ongoing strategic planning and review of organisational priorities and funding availability. The project status is red as there are no resources allocated to support continuation of this project.
Q4 24-25 | Fire Rescue Victoria | FRV | 3030 | Rostering and Shift Change | Emergencies and Safety | Systems Management | Purchase and implement a contemporary off the shelf Rostering and Shift Change system to replace multiple legacy systems. | Delivery | Efficiency/Productivity (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-06-26 | 2020-12-08 | 2021-09-14 | 2021-09-14 | 0 |  | 2021-09-15 |  | 2022-11-02 | 2026-06-30 | 3760000 | 4349947 | Amber | Amber | Amber | Amber | Amber | The solution implementation for the shift change and recall functionality for FRV Division A (metropolitan fire stations) has been delayed due to the need to confirm and agree on requirements with internal stakeholders. FRV Division B (regional fire stations) implementation has commenced and is progressing to plan. With the deliverables progressing as planned, and completion of Division B implementation, the project is expected to return to green.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 3033 | Victims of Crime Financial Assistance Scheme | Community Services | Customer Initiated Assistance | The Project will deliver an ICT system centred around Case Management to deliver funds and support to Victims of Crime. The system will underpin the new financial assistance scheme approved by Cabinet. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Project Management Excellence | 2019-01-04 | 2021-06-30 | 2023-12-30 | 2023-12-30 | 3297000 | 2971000 | 2024-03-01 |  | 2025-06-30 | 2025-07-30 | 18423392 | 16338623 | Amber | Amber | Amber | Amber | Amber | The Financial Assistance Scheme (FAS) went live successfully on 18 November 2024, with core functionality delivered. Further systems development has been extended into July 2025 due to adjusted and refined requirements. Migration of legacy data into the new system has commenced and operational use of the new functionality is planned for August 2025.
Q4 24-25 | Wannon Region Water Corporation | WAN Water | 3091 | Billing and Customer Relationship Management Systems | Environment and Water | Customer Relationship Management | The replacement of the organisation's Billing and Customer Relationship Management Systems | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2020-01-01 | 2021-03-31 | 2022-06-24 | 2022-06-24 | 100000 | 650000 | 2022-08-15 | 2023-01-03 | 2024-03-22 | 2026-06-30 | 8200000 | 10251000 | Amber | Amber | Amber | Amber | Amber | The project is rated amber due to a tight schedule for the new procurement process.
Q4 24-25 | Goulburn Valley Region Water Corporation | GVR Water | 3130 | Billing and Customer Relationship Management System | Environment and Water | Customer Relationship Management | The project will replace Goulburn Valley Water's existing legacy billing and CRM systems with a modern, efficient and customer focused system | Initiated |  |  | Internal project management methodology | 2018-10-01 | 2021-06-30 | 2026-06-30 |  | 75000 | 487457 | [11 empty] | GVW is planning to go to market seeking a consultancy to update and revise the Business Case and revisit the Sourcing Strategy for this project which will be presented to The Board by 3rd Quarter FY 25/26.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 3168 | Post Sentence Authority Case Management System | Law and Justice | Tracking and Workflow | A case management system, crucial to sustainable operations and managing the risks associated with manual information flow, will be delivered. Real time information will be provided for informed decisions about offenders to uphold community safety. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2021-03-30 | 2021-07-15 | 2023-06-30 | 2023-06-30 | 150000 | 213455 | 2024-03-01 |  | 2025-12-31 | 2026-06-01 | 1878947 |  |  |  | Amber | Amber | Green | The project has commenced an additional discovery phase in collaboration with the vendor, who will deliver updated business requirements, a detailed solution architecture design, and a refined implementation proposal that includes timeline and effort estimates. The integration design has been revised following input from the vendor, third-party stakeholders, and other relevant technical experts to ensure alignment with the overall solution.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 3170 | Technology and resources to support Victoria’s fines system | Law and Justice | Systems Management | Delivery of next generation of fines platform by incrementally implementing functions into the business landscape to complement existing technology, ensuring better revenue collection, assistance for vulnerable Victorians and debtor-centric services. | Delivery | Customer Satisfaction (Non Financial), Increased Revenue (Financial) |  | Hybrid - Waterfall and Agile | 2021-03-10 | 2021-08-30 | 2021-12-16 | 2021-12-16 | 0 | 10367000 | 2022-01-09 | 2022-01-01 | 2025-06-30 | 2026-06-30 | 131615000 | 169961000 | Amber | Amber | Amber | Amber | Red | The project has continued its analysis for more efficient, alternative delivery approaches to meet the current timelines. The project is reporting its status as Red due to schedule pressure, with the program's delivery velocity trailing forecast outcomes. The program has made some interim delivery approach adjustments, transitioning to shorter delivery cycles to improve throughput while the more detailed analysis continues.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 3171 | Better Technology Tools Enabling Responsibility (BTTER) | Law and Justice | Development and Integration | Deliver applications to automate processes, reduce costs and risks associated with existing manual systems for safety benefits. Prison management systems will be uplifted, and rehabilitation and reintegration services will be enhanced. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2020-07-21 | 2021-02-19 |  | 2021-02-19 | 324114 |  | 2021-02-22 |  | 2023-06-30 | 2029-06-30 | 18868800 | 54066710 | Green | Green | Green | Green | Green | The project is tracking well against budget, schedule and scope. Additional budget has been secured, and the delivery end date has been revised from June 2025 to June 2029. This will enable a strategic path for the program to deliver the product enhancements in a wider rollout across the state,
Q4 24-25 | Department of Government Services | DGS | 3199 | RTBA - Bond Management System Replacement | Community Services | Customer Relationship Management | This project will deliver an enhanced, updated solution to the Residential Tenancies Bond Authority legacy systems which are reaching end of life. The solution will ensure alignment to the business vision. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2021-04-12 | 2021-12-31 | 2021-12-31 | 2022-02-28 | 975000 |  | 2022-03-01 |  | 2023-06-30 | 2026-06-30 | 8900000 | 10394000 | Amber | Amber | Amber | Amber | Amber | The project has expanded its scope to include portable bonds scheme (PBS). The revised budget and schedule are to support the additional PBS scope. The project reported Amber as it is currently finalising PBS requirements.
Q4 24-25 | Melbourne Water | MELB Water | 3214 | Strategic Relationship Management Tool Phase 1-2 | Environment and Water | Collaboration | To enhance delivery of business goals by improvement in business capabilities and relationship management tools to allow ongoing management and continuity of relationships to achieve strategic improvements in organisational goals. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2020-11-25 | 2021-08-01 |  | 2021-11-04 | 0 |  | 2021-11-04 |  | 2022-06-28 | 2026-05-28 | 3174023 |  | Green | Green | Green | Green | Green | As at 20250630: RFQ closes in July. Workshops in progress to confirm current workflows, project budget and schedule to be reconfirmed post RFP process.
Q4 24-25 | Victorian Institute of Forensic Medicine | VIFM | 3241 | Replace Case Management System | Law and Justice | Customer Relationship Management | Case Management System will be replaced to meet current and future business and reporting requirements. The project delivers a contemporary solution to support forensic investigations for Victoria’s justice system. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-07-01 | 2022-01-07 |  | 2022-01-07 | 0 | 350000 | 2022-01-07 |  | 2023-12-31 | 2025-08-19 | 5650000 | 6150000 | Amber | Green | Green | Green | Green | The project is on track for completion in August 2025. The scope is expected to be delivered within budget
Q4 24-25 | Victorian Institute of Forensic Medicine | VIFM | 3242 | ICT Infrastructure Migration to the Cloud | Law and Justice | Systems Management | The Cloud Migration project will transfer VIFM forensic services information from aging ICT infrastructure to the Cloud. The project improves the security, efficiency, and resilience of VIFM’s forensic information for Victoria’s justice system. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-07-01 | 2022-06-30 | 2022-01-03 | 2022-01-03 | 0 | 585000 | 2022-01-03 |  | 2024-06-30 | 2025-06-30 | 2338000 | 3261000 | Green | Green | Green | Green | Green | The project has completed Phase 1 on schedule and budget. Phase 2 will be completed with the transition of the VIFM Case Management System to a new cloud-based solution, which is funded under the project’s recurrent budget. No further work is required as part of this project scope and budget to finalise the migration.
Q4 24-25 | Fire Rescue Victoria | FRV | 3254 | FRV Operational Station Connectivity | Emergencies and Safety | Assets/Materials Management | The implementation of the FRV network and FRV Station Turn Out systems across ex CFA stations. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-09-01 | 2021-03-23 |  | 2021-03-23 | 0 |  | 2021-03-25 |  | 2023-06-30 | 2026-08-17 | 16689890 | 18418852 | Green | Green | Green | Green | Amber | Delivery timelines have been impacted by internal resourcing priorities changing and external factors, including construction approval delays, site conditions, and vendor-to-vendor coordination issues. Assuming existing internal resources remain allocated, the planned delivery date is achievable based on the defined path to green, which is contingent on maintaining consistent program resourcing. Progress toward this will be closely monitored.
Q4 24-25 | Department of Health | DH | 3261 | Health Information Exchange (HIE) | Health | Data Management,Development and Integration | Deliver a Health Information Exchange for secure sharing of pathology information at the Point of Care, and to facilitate planning for increased scope/budget in subsequent years to cater for all key clinical domains for VPHS state-wide rollout. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-06-01 | 2021-06-30 |  | 2021-06-30 | 0 |  | 2021-07-01 |  | 2025-06-30 | 2025-12-31 | 27220000 | 26026574 | Amber | Amber | Amber | Red | Red | Project is progressing but unable to meet original planned end date due to technical issues and constraints in accessing required services. As a result the schedule has been extended and work is continuing to resolve these issues.
Q4 24-25 | Melbourne Water | MELB Water | 3270 | Audio Visual Remediation | Environment and Water | Collaboration | Melbourne Water has a requirement to update Audio-Visual solutions in meeting rooms across multiple sites in Victoria that will provide a consistent experience for all users and allow for enhanced collaboration. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2021-07-08 | 2021-12-03 | 2022-01-20 | 2022-01-20 | 0 |  | 2022-01-20 |  | 2023-01-10 | 2025-11-05 | 2424764 |  | Green | Green | Green | Green | Amber | As at 20250630: The project scope is amber due to the RFQ process and requirements clarification is in progress. Once finalised and order confirmed a Change Request will be submitted and the schedule will be realigned.
Q4 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 3278 | People and Payroll Transformation Program - Rostering Project | Health | Human Capital / Workforce Management ,Human Resources | The People Systems Program will deliver a Rostering solution which will increase efficiency and improve data security and integrity by eliminating paper time sheets and manual processes. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2021-09-01 | 2022-07-01 | 2023-08-02 | 2023-08-02 | 50000 | 500000 | 2023-08-03 |  | 2025-06-30 | 2025-12-31 | 6428267 | 9259900 | Green | Green | Green | Green | Green | System Integration Testing is continuing with in depth testing across the entire system functionality.
Q4 24-25 | Oral Health Victoria | OHV | 3280 | Electronic Oral Health Record (EoHR) | Health | Development and Integration | The Electronic Oral Health Record (EoHR) aims to replace and consolidate the legacy solution to deliver a single state-wide oral health record to support improved dental health outcomes in Victoria | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-04-01 | 2020-10-30 |  | 2020-10-30 | 390000 |  | 2021-09-22 |  | 2023-06-30 | 2025-12-19 | 9490000 |  | Amber | Amber | Amber | Amber | Amber | R1 project was delivered. Project resources onboared for R2 planning, and commencement of engagment approach with business and sector.
Q4 24-25 | Department of Transport and Planning | DTP | 3312 | Smarter Roads Program - Timetable Systems Uplift | Transport and Vehicles | Content Management,Data Management,Systems Management | Objective of this project is to prepare an options analysis brief outlining best of breed solutions for Timetabling and Journey planning. The analysis will inform a recommended solution to build and implement. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-03 | 2021-12-30 | 2022-02-07 | 2022-02-07 | 0 |  | 2022-02-07 |  | 2023-03-31 | 2025-09-18 | 4739268 | 6716680 | Amber | Amber | Amber | Green | Amber | The project status is reported as amber due to solution implementation issues impacting the project schedule. The project team is working on mitigating these issues to get the project back on track.
Q4 24-25 | Department of Transport and Planning | DTP | 3318 | Automatic Vehicle Monitoring Sustainment (AVMS) | Transport and Vehicles | Systems Management | Address key short-term challenges affecting Melbourne’s tram network through targeted initiatives to sustain the AVM system in the short-term while the Department continues to develop options for a future Tram Monitoring and Control (TMC) system. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PTV Investment Lifecycle | 2021-07-01 | 2022-04-29 | 2023-08-30 | 2023-08-30 | 1785000 | 0 | 2023-08-31 |  | 2025-06-30 | 2026-03-30 | 32018000 |  | Amber | Amber | Green | Green | Green | The AVMS On Board project is progressing well through testing activities, and is on track to commence implementation in 2025.
Q4 24-25 | Fire Rescue Victoria | FRV | 3325 | Human Resources Information System (HRIS) | Emergencies and Safety | Human Resources | HRIS Project has the primary focus this year to address foundation data issues, collaborate with the Rostering and Shift Change project and build a business case for approval. Scope includes Payroll and HR | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | FRV Project Management Framework (PMF) | 2021-12-10 | 2022-06-30 | 2023-02-28 | 2023-02-28 | 0 | 0 | 2023-03-01 |  | 2025-03-01 | 2026-09-16 | 22392000 |  | Amber | Amber | Amber | Green | Amber | Tender evaluation is currently underway and progressing as planned. The funding for the program is being finalised through a business case, resulting in a red cost status until the funding has been resolved. The funding position is posing a significant risk to the schedule, resulting in an amber overall status rating.
Q4 24-25 | South West Alliance of Rural Health | SWARH | 3334 | Regional Electronic Health Record Upgrade (excluding Barwon Health) | Health | Customer Relationship Management,Data Management,Development and Integration ,Management of Process ,Records Management ,Systems Management,Tracking and Workflow | Upgrade to the regional Electronic Health Record (EHR) solution, that supports 11 health services across South West Victoria. The project will improve clinician and patient user experience, focusing on quality and safety of patient care. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2019-10-16 | 2022-03-31 | 2022-08-31 | 2022-09-01 | 180000 | 300000 | 2022-09-05 |  | 2025-06-30 | 2027-04-01 | 23495000 |  | Amber | Green | Red | Red | Green | Project delivery is advancing in line with the revised schedule, with targeted actions in place to address remaining scope and quality risks.
Q4 24-25 | Melbourne Water | MELB Water | 3338 | Electronic Content Management Phase 1 | Environment and Water | Content Management | This project will upgrade Melbourne Waters current document storage repositories and migrate to a new Electronic Document and Records Management System (EDRMS) | Initiated |  |  | PMBoK | 2021-10-08 | 2022-09-22 | 2025-09-11 |  | 0 | [12 empty] | As at 20250630: Business Case due for submission in September.
Q4 24-25 | Victoria Police | VicPol | 3358 | Electronic Document and Records Management System | Law and Justice | Document Management | The overall objective of the project is to implement a fully integrated, enterprise-wide Electronic Document and Records Management Solution and an Enterprise Service Management platform to uplift information management maturity. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-25 | 2024-12-31 | 2025-12-31 | 8559000 | 8559000 | Green | Green | Green | Green | Green | The project status remains ‘Green’. The core objective of the Business Case has been achieved and the EDRMS (Records365) has been delivered by 31 March 2025. The project is ongoing until 31 December 2025 in order to deliver and embed supporting products as part of the overall solution suite.
Q4 24-25 | Victoria Police | VicPol | 3359 | Finance Systems Program (Oracle Cloud) | Law and Justice | Investment Management | Delivery of a new financial system, updating technology and business processes across finance, purchasing and supply chain functions to increase efficiency and improve access to accurate information to support decision-making. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2021-11-25 |  | 2025-06-30 |  | 32453000 |  | Red | Red | Red | Red | Red | Key risks relating to schedule and budget have been identified and are being actively monitored. Contract has been signed with implementation partner for the Detailed Design Phase. Onboarding of team members and knowledge transfer has been completed. Work is underway to finalise and baseline the detailed, integrated schedule.
Q4 24-25 | Victoria Police | VicPol | 3360 | Enterprise Rostering | Law and Justice | Human Capital / Workforce Management | The project will deliver an enterprise wide rostering and timesheet solution, consolidating disparate systems and manual processes into one integrated system to better support rostering and timesheet management. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2020-10-15 | 2020-11-24 |  | 2020-11-24 | 0 |  | 2020-11-25 | 2021-11-24 | 2024-12-31 | 2025-09-30 | 21490000 | 21490000 | Red | Red | Red | Red | Red | Key risks relating to scope, schedule and project budget have been identified and are being monitored. The project is rated 'red' as it is not tracking for completion by the current delivery end date of September 2025. The project schedule will be re-baselined after the Request for Proposal process.
Q4 24-25 | Country Fire Authority | CFA | 3369 | CFA Radio Replacement Program | Emergencies and Safety | Communication | CFA’s current Tait 9100 series radios are no longer manufactured and are approaching the end of their practical life for operational purposes. These will be replaced across Victoria and will introduce a technology refresh with enhanced functionality. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2021-07-01 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 235465 | 235465 | 2022-04-01 |  | 2024-06-30 | 2025-09-30 | 138595535 | 136247000 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q4 24-25 | Department of Government Services | DGS | 3377 | Digital Victoria Marketplace | Government and Economy | Collaboration ,Data Management,Records Management | The Marketplace is an initiative by Digital Victoria to provide a simpler, and easier way for Government and Industry to interact through the eServices register and various other SPC's. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-01 | 2021-10-13 |  | 2021-10-13 | 0 | 7708 | 2022-02-01 |  | 2027-06-30 |  | 16790000 |  | Green | Green | Green | Green | Green | The digital marketplace is meeting agreed timelines for releasing functionality into the production version of Digital marketplace which aligns with the expected benefit delivery throughout the 24/25FY
Q4 24-25 | Alfred Health | ALFRED | 3378 | Alfred Health / Monash Health - Shared Laboratory Information System | Health | Records Management | The shared LIS program will deliver a Laboratory information system as a foundational technology for the Alfred Monash Pathology partnership supporting the DoH Pathology sector reform initiative to consolidate pathology systems and services. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-10-05 | 2022-08-31 | 2023-02-28 | 2023-02-28 | 2000000 | 2000000 | 2023-02-28 |  | 2025-06-30 | 2026-06-30 | 25000000 | 33000000 | Amber | Amber | Amber | Red | Red | The program is off track due to various issues relating to project schedule, finances, and resource challenges. The project team has developed a recovery plan and re-baselined schedule, subject to approval by the Project Steering Committee in July 2025.
Q4 24-25 | Department of Transport and Planning | DTP | 3399 | Victraffic Upgrade Project | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Preferences | Objective of this project is to support transport users and emergency response units to safely and confidently move around our road network during an emergency situation and improve road closure capture and uplift the user experience. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-27 | 2022-09-19 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-10 |  | 2024-06-30 | 2026-06-30 | 22637000 |  | Green | Green | Green | Green | Green | The overall status is green, and the project is on track with all implemented systems in the process of being transitioned to operations.
Q4 24-25 | Court Services Victoria | CSV | 3451 | Victorian Civil and Administrative Tribunal digital service transformation | Law and Justice | Content Management,Customer Initiated Assistance,Development and Integration ,Security Management ,Tracking and Workflow,Data Management,Document Management ,Forms Management,Knowledge Management ,Management of Process ,Records Management ,Routing and Scheduling | The project aims to upgrade digital services infrastructure including the case management system and increase process automation, to deliver more accessible and timely provision of justice to citizens and businesses | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - Waterfall and Agile | 2020-11-01 | 2021-02-04 |  | 2021-05-15 | 0 |  | 2021-07-01 | 2021-07-01 | 2024-12-01 | 2025-12-01 | 56681000 |  | Amber | Amber | Amber | Amber | Amber | Rollout of the new Rental Dispute Resolution Victoria (RDRV) service which includes the self-service portal myRDRV and RDRV website will provide renters and rental providers resolve conflicts faster. Launch of a new call centre technology which will provide better service for those who contact RDRV. Reporting Amber as the timelines and requirements of the remaining lists that will be built in the new Case Management System (CMS) needs to be understood and the long procurement process encountered when commencing the Data Fabric project with our information technology partner.
Q4 24-25 | CenITex | CenITex | 3452 | Legacy Hardware Refresh | Government and Economy | Assets/Materials Management | The project will refresh the core network infrastructure in the data centres, ensuring the infrastructure platform is supported and robust to meet the demands of Cenitex customers. | Closed - Completed | Cost Reduction (Financial), Risk Reduction (Non Financial) | 2025-06-30 | PRINCE2 | 2021-11-15 | 2022-05-05 |  | 2022-05-05 | 0 |  | 2022-05-05 |  | 2023-06-30 | 2025-06-30 | 4049735 | 6069833 | Green | Green | Green | Green | Green | Project Completed.
Q4 24-25 | Victorian Institute of Forensic Mental Health (Forensicare) | Forensicare | 3458 | Human Capital Management (HCM) Rostering Payroll System | Health | Human Capital / Workforce Management ,Human Capital / Workforce Management | Forensicare is implementing a new Human Capital Management system to replace and integrate its ageing payroll, rostering and recruitment systems. This system will better meet staff needs and improve capacity for better care to growing customer base | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2021-08-23 | 2022-09-08 | 2023-12-11 | 2023-12-11 | 0 | 221000 | 2024-01-15 |  | 2025-09-30 |  | 2580000 |  | Green | Green | Green | Green | Amber | Planning the next phase is underway with the remaining functionality to be implemented including - Learning Performance Engagement Succession Rostering Time and Attendance and Payroll.
Q4 24-25 | V/Line Corporation | V/Line | 3465 | Payroll Improvements | Transport and Vehicles | Human Capital / Workforce Management | The objective of the payroll improvement project is to improve data collection for Leave, Time & Attendance information to support V/Line’s payroll function, in creating a more robust and consistent payroll operation organisation wide. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2023-03-31 | 2024-05-31 | 2024-05-31 | 0 | 500000 | 2024-06-03 | 2024-12-09 | 2025-09-30 | 2025-12-23 | 3300000 |  | Green | Green | Amber | Green | Green | The project team commenced the evaluation of time and attendance solutions within Human Capital Management solutions in Q4 whilst preparing procurement documentation to review best of breed time and attendance solutions to ensure the best solution is selected for V/Line.
Q4 24-25 | Central Highlands Region Water Corporation | CHR Water | 3466 | Digital Metering Program | Environment and Water | Customer Initiated Assistance,Customer Relationship Management | Replace analogue meters with digital, resulting in improved customer experience, reduced operational risk, improved environmental and sustainability footprint, and utilise water meter data to provide greater oversight of the water and sewer network. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2020-07-01 | 2022-12-31 |  | 2023-01-02 | 0 |  | 2023-01-02 |  | 2026-09-30 |  | 19500000 | 20419619 | Green | Green | Green | Green | Green | Project proceeding to stakeholder expectations
Q4 24-25 | Austin Health | AH | 3494 | Austin Health HR Information Systems | Health | Human Resources | The HRIS project will replace legacy HR Systems for Payroll, Recruitment and On-boarding systems to modernise processes and introduce efficiencies at Austin Health. | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial) | 2025-04-30 | PRINCE2 | 2022-07-31 | 2023-02-01 |  | 2023-02-01 | 0 |  | 2023-02-01 |  | 2024-06-30 | 2025-04-30 | 7800000 | 11043528 | Amber | Amber | Amber | Green | Green | Hypercare complete. Business readiness complete. Closed
Q4 24-25 | Melbourne Health | Melb H | 3496 | Parkville Laboratory Information System (LIS) Program | Health | Management of Process ,Records Management ,Systems Management,Tracking and Workflow | The LIS Connect Program will procure and implement a single LIS solution for Pathology Network West across the Parkville precinct pathology services. Stage 1: LIS planning and procurement Stage 2 (delivery): LIS implementation | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-03-01 | 2023-12-31 | 2024-07-31 | 2024-07-31 | 6047518 |  | 2024-09-23 |  | 2026-08-28 |  | 23817159 |  |  | Green | Green | Amber | Amber | Mitigating actions to bring the core LIS design and build activities back on track have been successful, however has exacerbated the resource demand for the project.
Q4 24-25 | Department of Transport and Planning | DTP | 3497 | Victorian Transport Digital Engineering Transformation Program | Transport and Vehicles | Assets/Materials Management,Content Management,Data Management,Document Management ,Visualisation | Objective of this project is to develop a roadmap to progressively move to a digital environment for engineering, design and data management. DoT and MTIA will collectively deliver the DE Transformation, Horizon 1 -3 projects over the next 2-3 years. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2022-12-30 | 2023-02-06 | 2023-02-06 | 0 |  | 2023-02-06 |  | 2023-12-29 | 2025-12-31 | 5135000 | 45000518 | Amber | Green | Green | Green | Amber | The program is reporting an amber status as it is experiencing budget pressure on several potential pilots, with replanning occurring to ensure value is obtained from the pilots.
Q4 24-25 | Department of Transport and Planning | DTP | 3502 | Speed Change Management Tool Project | Transport and Vehicles | Communication,Content Management,Data Management | This project streamlines speed zone and sign changes with an integrated tool enabling councils and agencies to easily submit and track requests, resulting in faster, more consistent speed changes across Victoria, contributing to enhanced road safety. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-08-01 | 2023-01-31 | 2023-04-28 | 2023-05-08 | 0 |  | 2023-06-19 |  | 2024-07-31 | 2025-06-30 | 1029000 |  | Green | Green | Green | Green | Green | The project is now completed.
Q4 24-25 | Fire Rescue Victoria | FRV | 3505 | Implementing Protective Marking and Information Protection | Emergencies and Safety | Data Management | Implementing processes for managing protective markings on official or higher classified content (documents and emails) in line with the Office of the Victorian Information Commissioner : Victorian Protective Data Security Standards. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2022-02-11 | 2022-06-30 |  | 2022-06-30 | 0 |  | 2022-07-01 |  | 2024-06-30 | 2026-06-30 | 1512000 |  | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q4 24-25 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3518 | Project Synergy | Employment, Skills and Workplace | Development and Integration | This project will consolidate applications, retiring 18 applications and 8 databases, moving to a new single database using Microsoft Dynamics 365 which will reduce implementation processing times, improved data accuracy and processes. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-05-12 | 2022-12-09 |  | 2022-12-09 | 628000 |  | 2023-02-06 |  | 2024-02-06 | 2024-09-30 | 2036760 | 2225430 | Amber | Red | Red | Red | Red | Project closed with a reduced scope and benefits profile delivered. Phase 1 is live with a new CRM embedded into the organisation, discovery and design for Phase 2 & 3, single system database, complete.
Q4 24-25 | Peninsula Health | PEN Health | 3522 | Peninsula Health NHCA Smart Ward | Health | Business Intelligence | National Centre for Healthy Aging (NCHA), a Monash University (MU) and Peninsula Health (PH) collaboration, has established a program of works that includes the establishment of a Smart Ward to collect patient observations for Research. | Delivery | Customer Satisfaction (Non Financial) |  | PRINCE2 | 2022-11-07 | 2023-01-31 | 2024-02-29 | 2024-03-07 | 0 | 19968 | 2024-03-07 |  | 2025-07-31 | 2025-12-31 | 1222641 | 1423459 | Green | Green | Green | Green | Green | Progress remains steady with significant progress made with installing equipment nearly completed. Project remains on track.
Q4 24-25 | Ambulance Victoria | AVS | 3547 | Cloud & Infrastructure Program | Health | Assets/Materials Management | The program will upgrade network infrastructure and address the closure of data centres and the end-of-life of data centre assets through migrating workloads to Cloud. This program will deliver improved security and performance for our services. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-04 | 2023-01-31 |  | 2023-01-31 | 341911 | 155621 | 2023-02-01 |  | 2025-11-28 | 2027-06-30 | 18295989 | 14522917 | Green | Green | Green | Green | Green | The project is reporting as green and delivery is progressing as planned.
Q4 24-25 | Royal Children's Hospital | RCH | 3551 | Identity and Access Management (IDAM) | Health | Security Management | Implementation of new identity management solution | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-11-28 | 2023-06-02 | 2025-01-23 | 2025-01-23 | 0 |  | 2025-01-23 |  | 2025-12-31 |  | 3368053 |  |  |  |  | Green | Green | Project is tracking well. Focus for current period is on integration with key systems, ServiceNow and SAP. Successful integration with these solutions is critical to project success. We hope to have the work planned out shortly.
Q4 24-25 | Melbourne Water | MELB Water | 3557 | HR Modernisation | Environment and Water | Human Resources | Implement new Human Resources Information System (HRIS) technology to provide a sustainable, efficient and contemporary solution for people and payroll management, people performance and learning organisation goals. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2025-06-30 | PMBoK | 2022-10-05 | 2023-08-31 | 2023-11-13 | 2023-12-13 | 0 |  | 2023-12-13 |  | 2024-11-19 | 2025-08-15 | 2722712 | 6892613 | Green | Green | Green | Green | Red | As at 20250630: Project postponed to reassess approach to ensure we achieve business benefits.
Q4 24-25 | Melbourne Water | MELB Water | 3559 | Network Architecture Improvements SDWAN | Environment and Water | Security Management | Network Architecture improvement to SD WAN / Zero trust Model | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | PMBoK | 2021-08-26 | 2023-01-16 |  | 2023-01-25 | 0 |  | 2023-01-26 |  | 2023-10-10 | 2026-12-09 | 1189517 | 3470123 | Green | Amber | Red | Red | Red | As at 20250630: Project preparing to commence pilot design for Phase 2. Project is red due to impacts of redesign required for new solution. This redesign will ensure the solution provides greater resilience than the original solution. A Change Request will be submitted to rebaseline the project. in Q1 FY25/26.
Q4 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3563 | Regional integrated Electronic Patient Record | Health | Records Management | Delivery of an integrated Electronic Patient Record for members of the Loddon Mallee Rural Health Alliance (excluding Bendigo Health) - this will support more connected patient care for patients region wide. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-03 | 2023-06-30 | 2026-01-30 |  | 70000 | 600000 | [11 empty] | Due to scope potentially broadened to entire Loddon Mallee Region, revised date for detailed costings and agreed approach is Q1 2026.
Q4 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 3567 | Wireless Network Refresh | Health | Collaboration ,Communication,Systems Management | The project will deliver a modernized wireless network infrastructure at the Victorian Comprehensive Cancer Centre (VCCC), replacing outdated hardware with advanced, high-performance equipment. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-10-20 | 2023-07-31 | 2023-08-14 | 2023-08-14 | 0 | 48807 | 2023-08-15 |  | 2025-01-31 | 2025-08-31 | 1600929 | 1215457 | Green | Green | Green | Green | Green | Moved by 2 months to accommodate for hypercare clearing outstanding invoices and project closure
Q4 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3575 | Patient Administration System Replacement | Health | Data Management,Records Management ,Reporting | Replacement of Bendigo Health's current Patient Administration System (PAS) solution to align with the Electronic Patient Record (EPR) - moving to a single for both capabilities will ensure smoother patient care and support. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-06 | 2023-06-30 | 2023-09-30 | 2023-10-02 | 150231 |  | 2023-10-23 |  | 2025-07-15 | 2026-04-30 | 4930809 |  | Amber | Amber | Amber | Amber | Red | Project is reporting red due to delays to schedule as a result of late start of and lengthening of a number of project activities. Additional scope items have also been identified by clinical functional review workshops and will need to considered and tabled at the relevant governance committee/s.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3577 | Expanding Victoria's Waste Data Systems | Environment and Water | Data Management | The project will deliver new Victorian Circular Economy metrics and expand Victoria’s Waste Data System for the Victorian economy, ensuring reliable, useful and timely data. | Closed - Completed | Compliance (Non Financial) | 2025-06-30 | Governance by Sustainability Fund reporting and review | 2020-10-06 | 2021-07-01 |  | 2021-07-01 | 4668000 | 0 | 2021-07-01 |  | 2024-06-30 | 2025-06-30 | 2438000 | 7106000 | Amber | Amber | Green | Green | Green | Data has been migrated from legacy systems to Recycling Victoria systems on DEECA tenancy, this is the final milestone for the project. The project is complete.
Q4 24-25 | Department of Transport and Planning | DTP | 3584 | Heavy Vehicle - Structural Assessment and Permit System (HV-SAPS) | Transport and Vehicles | Customer Initiated Assistance,Management of Process ,Tracking and Workflow | The project delivers automation capability for Class 1 vehicle permit assessments, to enable automatic processing for 85% of permits to streamline approvals for the heavy vehicle industry, and reduce reliance on manual processing & contingent workers | Closed - Completed | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) | 2025-04-03 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-01-11 | 2023-03-31 | 2023-12-18 | 2023-12-18 | 0 |  | 2023-12-18 |  | 2024-09-20 | 2025-04-03 | 6297993 |  | Green | Amber | Green | Green | Green | The project delivery has been completed.
Q4 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3585 | Regional Community Care Coordination Platform | Health | Records Management ,Tracking and Workflow | Delivery of a digital medical record for all the Community health care provided by members of the Loddon Mallee Rural Health Alliance to support connected patient care across the region (and between health services). | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2018-07-01 | 2019-04-01 |  | 2019-04-10 | 0 |  | 2019-04-11 |  | 2021-03-31 | 2026-02-27 | 1330000 | 4528817 | Green | Green | Green | Green | Amber | Amber reporting status due to delay in transition activities to accommodate extension to Support at Home program to November 2025.
Q4 24-25 | CenITex | CenITex | 3596 | Enterprise platforms renewal program | Government and Economy | Customer Relationship Management | Upgrade existing Dynamics 365 platform and implement a system that integrates & meets stakeholder requirements for Customer Engagement Project Services and Finance. Also, mitigate support issues due to end of life of the current platform. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-01-04 | 2023-01-12 |  | 2023-01-12 | 0 |  | 2023-02-03 |  | 2024-06-28 | 2025-08-31 | 1652000 | 1817347 | Green | Green | Green | Green | Green | Project is tracking to plan.
Q4 24-25 | Department of Health | DH | 3599 | Mental Health and Wellbeing Website | Health | Communication | This project will deliver a mental health website, addressing recommendations 6.4 and 31.3 of the Royal Commission into Victoria's Mental Health System, to help Victorians navigate the mental health system and find relevant services and supports. | Postponed |  | 2023-06-30 | Agile | 2022-09-21 | 2023-05-12 | 2023-06-30 |  | 843493 | 1185694 |  |  |  |  | 0 | [6 empty] | Project on pause due to priority being given to other mental health and wellbeing initiatives.
Q4 24-25 | South West Alliance of Rural Health | SWARH | 3602 | HR Digital Solution | Health | Human Resources | The scope of the strategic HRIS is to replace the Health Services HR applications and manual, paper-based processes with a contemporary, fit-for-purpose, strategic HRIS solution. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2023-02-24 | 2023-10-27 | 2023-12-01 | 2023-12-01 | 834297 |  | 2024-01-15 |  | 2026-04-30 |  | 13629603 |  | Green | Green | Amber | Red | Red | Project continue to rely on the key dependency of the roll out of the rostering project. The project continues to scope new integrations and is working with the vendor to determine a path to enter the testing phase
Q4 24-25 | Department of Premier and Cabinet | DPC | 3608 | Workflow Management System for Office of Chief Parliamentary Counsel (OCPC) | Government and Economy | Development and Integration ,Tracking and Workflow | WMS project will provide workflow for managing legal projects to improve management of the projects as per the OCPC standards and timely and accurate reporting to internal and external users to ensure timely publishing on the legislation website. | Postponed | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) | 2025-05-09 | Agile | 2021-06-18 | 2021-07-01 |  | 2021-07-01 | 0 |  | 2023-02-24 |  | 2024-07-13 | 2026-11-20 | 2500000 |  | Amber | Amber | Green | Red | Red | The project is under review due to some complexities and vendor resourcing constraints.
Q4 24-25 | Central Highlands Region Water Corporation | CHR Water | 3612 | ERP Upgrade | Environment and Water | Assets/Materials Management,Financial Management,Human Capital / Workforce Management ,Supply Chain Management | This project will upgrade the existing platform(s) due to an impending end of support timeline with a contemporary integrated solution to improve the Finance, Procurement, Commercial and Asset Management processes of CHW | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-01-02 | 2023-06-30 | 2023-09-29 | 2023-09-29 | 0 |  | 2023-10-02 |  | 2025-09-30 | 2026-04-17 | 9510000 | 10162829 | Green | Green | Green | Green | Green | Re-planning for Stage 2/3 of the project completed in this quarter resulting in some changes to the schedule and costs. Stage 2 activities commenced in May
Q4 24-25 | Department of Health | DH | 3615 | OurService Extensions | Health | Forms Management,Tracking and Workflow | Deliver multiple enhancements to ServiceNow platform, including migration of additional new services and integration with other major corporate systems, that further improves the consistency and customer experience of service. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | Agile | 2022-10-03 | 2023-05-26 |  | 2023-05-26 | 302604 |  | 2023-05-26 |  | 2024-06-30 | 2025-06-30 | 2365565 | 2987934 | Amber | Green | Green | Green | Green | Project has successfully delivered and closeout activities underway.
Q4 24-25 | Department of Premier and Cabinet | DPC | 3619 | Digital Records & Information Management Shared Services (DRIMSS) | Government and Economy | Content Management,Records Management ,Systems Management,Document Management | The project will implement an improved records and information management system to automate the records and information management process and comply with public records management requirements for the Department | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial) | 2025-06-30 | Agile | 2020-11-15 | 2021-06-25 |  | 2022-09-15 | 0 |  | 2022-12-05 |  | 2024-05-10 | 2025-06-30 | 2099521 | 2766399 | Green | Amber | Amber | Green | Green | The project has gone live in May 2025 and handed over to operation in June 2025. The project is now ready for closure activities
Q4 24-25 | Eastern Health | EH | 3638 | Enable Program | Health | Human Capital / Workforce Management ,Human Resources | Enable success of our people through 3 x HR systems projects: 1. Rostering Project - Replace RosterOn with Optima 2. People Journey Project - Replace eMercury with SAP SuccessFactors 3. Payroll Project - Replace SAP Payroll with SAP SuccessFactors | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-10-01 | 2023-03-31 |  | 2023-06-07 | 75000 |  | 2023-06-07 |  | 2025-10-31 | 2025-12-08 | 10148335 | 10592143 | Green | Green | Green | Green | Green | The Enable Program continues to run to the technical go live plan of both active projects with SuccessFactors already live. The Enable Program remains overall green but noting a slight delay in final go live for the final phase (phase 4) scheduled for late November/early December. Phase 4 is our biggest group involving Nursing & Midwifery.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 3642 | Digital Identity Uplift (Enterprise IDAM Uplift) | Employment, Skills and Workplace | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. Project name was changed from Enterprise IDAM Uplift | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-02-01 | 2023-03-31 |  | 2023-04-04 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-06-26 | 4316783 | 4229846 | Green | Green | Green | Green | Red | Schedule impacted due to critical infrastructure (servers) not being delivered on time. The project has successfully managed to contain the financial impact. Path to green involves raising a change request to extend the schedule.
Q4 24-25 | Monash Health | Monash H | 3644 | Security Card Technology Upgrade | Health | Security Management | Replacement of access control card readers and associated hardware across all sites to ensure access control security remains at an appropriate level and can integrate with current and future system requirements. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2022-04-15 | 2023-02-23 |  | 2023-02-23 | 0 |  | 2023-05-03 |  | 2024-05-31 | 2025-07-31 | 2263923 | 2519211 | Amber | Amber | Amber | Green | Green | The project is off track due to card testing not completed by the vendor as planned now scheduled for completion by 31 July 2025. All other planned activity completed.
Q4 24-25 | Grampians Rural Health Alliance | GRHA | 3645 | Maryborough Hospital Redevelopment ICT Project | Health | Development and Integration ,Systems Management | The Maryborough Hospital redevelopment ICT project provides infrastructure integration of clinical equipment mobile/desktop devices to support clinical care in the new state-of-the-art healthcare facility; improving care outcomes for patients. | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-12-01 | 2021-06-01 |  | 2021-06-01 | 0 |  | 2021-06-01 |  | 2025-06-30 | 2025-12-31 | 5158000 |  | Green | Green | Green | Green | Green | Final procurement packages in progress with key systems implementation nearing completion. Project is on track.
Q4 24-25 | Triple Zero Victoria | TZV | 3651 | Next Generation Computer Aided Dispatch System | Emergencies and Safety | Systems Management | Implement a new enhanced, reliable and secure emergency services Computer Aided Dispatch system to support enhanced critical emergency services 000 call taking and dispatch capability. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-07-01 | 2024-11-27 | 2024-12-01 | 20588172 |  | 2024-12-02 |  | 2027-06-30 | 2028-06-30 | 233301093 |  |  |  | Green | Green | Green | The project is tracking in accordance with scope, planned delivery cost and approved delivery schedule.
Q4 24-25 | Gippsland Health Alliance | GHA | 3654 | EMR Rural Expansion (Phase 4) | Health | Records Management | Expansion of EMR into 6 x Rural health services in the Gippsland Region | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | PMBoK | 2023-03-14 | 2023-11-30 | 2024-11-22 | 2024-11-22 | 200000 | 2675777 | 2025-03-12 |  | 2025-11-11 |  | 3383375 | [5 empty] | Green | The EMR Expansion project is tracking well—currently rated Green and actively progressing through the Delivery phase.
Q4 24-25 | Department of Families, Fairness and Housing | DFFH | 3658 | Integrated supervised contact and access solution | Community Services | Customer Relationship Management | Integrate existing case management and support systems (Contact & Access Transport System) for supervised contact and access to eliminate duplicate processes and better support planning and decision making for children in out of home care. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-15 | 2022-09-09 |  | 2022-10-13 | 0 |  | 2023-02-01 |  | 2024-06-30 | 2025-12-14 | 1217500 | 3277219 | Green | Green | Green | Amber | Green | Project is progressing to revised cost and schedule.
Q4 24-25 | Northern Health | NH | 3666 | Patient Engagement/Entertainment System (PES) | Health | Communication | To provide patient TVs and other supported clinical workflows for better patient care at Northern Health | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-11-02 | 2021-12-31 |  | 2021-12-31 | 50000 |  | 2023-02-01 | 2023-08-01 | 2024-07-30 | 2025-10-31 | 3450000 |  | Green | Amber | Amber | Green | Amber | The integration with Northern’s meal ordering system is progressing more slowly than anticipated due to technical complexities that have recently come to light. These issues are actively being worked through and the expectation is to bring the project back on track ahead of the next reporting period.
Q4 24-25 | Queen Elizabeth Centre | QEC | 3667 | Client Information Management System | Health | Data Management,Document Management ,Forms Management,Management of Process ,Reporting | QEC is focused on developing a Client Information Management System (CIMS) that can accommodate growth diversity and emerging evidence; enable clinical implementation of the outcomes framework; and meet funding and reporting requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-23 | 2023-10-18 | 2023-11-15 | 2023-11-29 | 225000 | 283153 | 2023-12-04 |  | 2025-12-30 |  | 1314347 | 1335472 | Green | Green | Green | Green | Green | Project is tracking as expected.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 3668 | EMD (Emergency Management Day) PHASE 2 | Law and Justice | Development and Integration | This project supports management of EMD data for remanded prisoners to avoid unlawful detention or release and reduce legal risk. The objective is to provide a system for SCWA to manage sentences prisoner discharges and documentation for CV. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Cost Reduction (Financial) |  | Agile | 2022-05-02 | 2023-03-31 |  | 2023-06-16 | 0 |  | 2023-03-31 | 2023-06-17 | 2024-06-30 | 2025-09-30 | 1466100 | 1466100 | Green | Green | Green | Green | Green | The project is tracking well against budget, schedule and scope.
Q4 24-25 | Melbourne Health | Melb H | 3683 | CMI Data Access Project | Health | Data Management,Records Management ,Reporting | The CMI Data Access Project will deliver the disaggregation of data contained in the Mental Health Client Management Interface (CMI). There will be four data repositories created to enable mental health program reporting for NH, WH, RMH and Orygen. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-07-01 | 2023-11-17 | 2023-09-04 | 2023-09-04 | 147800 | 80000 | 2023-09-04 |  | 2024-06-30 | 2025-11-28 | 1122200 | 1190000 | Green | Amber | Green | Green | Green | Project is tracking to the current schedule and budget
Q4 24-25 | Grampians Rural Health Alliance | GRHA | 3688 | Ballarat Base Hospital Redevelopment - ICT Program - Stage 3 | Health | Systems Management | Stage 3 will deliver ICT systems to support the project works, improving patient and staff systems & support. | Initiated |  |  | PMBoK | 2022-01-03 | 2025-12-01 | 2026-02-27 |  | 0 | [12 empty] | Project is continuing to scope IT deliverables and technical specifications.
Q4 24-25 | Hume Rural Health Alliance | HRHA | 3694 | ICT transition to Hume Rural Health Alliance (KDHS) | Health | Organisational Management | The project will transition Kyabram District Health Service (KDHS) ICT from Loddon Mallee Rural Health Alliance to Hume Rural Health Alliance to provide IT oversight and support. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-31 |  | 2024-04-24 | 100000 | 37000 | 2024-04-24 |  | 2025-06-30 | 2026-06-30 | 3463000 |  | Green | Amber | Amber | Amber | Amber | Project activities are on track based on rebaselined project plan with completion of numerous transition work such as IT support change over implementation of new Intranet site and out of support infrastructure upgrade. Transition approach for Payroll Time & Attendance platforms transition still to be determined. Multiple options have been considered previously with 2 presently being further discussed.
Q4 24-25 | Grampians Rural Health Alliance | GRHA | 3695 | MDHS ICT transition to Grampians Rural Health Alliance | Health | Organisational Management | The project will transition Maryborough District Health Service from Loddon Mallee Rural Health Alliance to Grampians Rural Health Alliance to better align with natural patient flows in the region (improved patient experience ). | Delivery | Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-11-17 | 2025-04-01 | 2025-04-01 | 0 | 150000 | 2025-04-01 |  | 2026-12-31 |  | 3450000 | [5 empty] | Green | Updated project management plan approved by the Department of Health. Key work packages for AD/Email/M365, unified communications and ICT support arrangements in progress. Project is on track.
Q4 24-25 | Loddon Mallee Rural Health Alliance | LMRHA | 3696 | HR Information System | Health | Human Capital / Workforce Management | Implementation of a Human Resources Information System (HRIS) for members of Loddon Mallee Rural Health Alliance -this uplift will enable resource planning and management visibility across the region. | Postponed | Compliance (Non Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) | 2024-09-19 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-12-31 |  | 2023-12-31 | 65000 | 175000 | 2024-01-01 | 2025-08-28 | 2025-12-20 | 2027-06-30 | 13500000 |  | Green | Amber | Amber | Amber | Amber | Amber status due to funding uncertainty as a funding source has not been confirmed. Funding alternatives are being explored with the regions.
Q4 24-25 | Transport Accident Commission | TAC | 3698 | Digital Identity Uplift | Transport and Vehicles | Systems Management | Uplift the Digital Identity environment to ensure people have the right access to resources, at the right time. This will enhance the user experience and strengthen security controls. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-05-18 | 2023-05-18 |  | 2023-05-18 | 0 |  | 2023-06-05 |  | 2025-06-30 | 2026-06-26 | 4316783 |  | Green | Green | Green | Green | Red | Schedule impacted due to critical infrastructure (servers) not being delivered on time. The project has successfully managed to contain the financial impact. A change request will be raised to extend the schedule.
Q4 24-25 | V/Line Corporation | V/Line | 3699 | HRIS (Human Resources Information System)​ system replacement | Transport and Vehicles | Human Capital / Workforce Management ,Human Resources | To implement a new human resource information system for V/Line, in order to improve accuracy and reliability of HR data for service delivery. | Initiated |  |  | PRINCE2 | 2023-07-01 | 2024-11-29 | 2025-09-30 |  | 900000 | 1462500 | [11 empty] | The Request for Proposals were released as planned in Q4 with assessment currently underway to procure a Human Capital Management System for V/Line and a System Implementation Partner to support the implementation of the solution selected.
Q4 24-25 | Triple Zero Victoria | TZV | 3700 | Emergency Sector Integration Platform | Emergencies and Safety | Systems Management | Provide a new single, vendor agnostic integration platform to interface into multiple 000VIC data sources that provides reliability and meet current and future anticipated requirements. Integrate CAD to current ESO systems. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Project Management Excellence | 2021-08-09 | 2021-12-28 | 2024-02-28 | 2024-02-29 | 570406 | 1400264 | 2024-02-29 |  | 2024-12-31 | 2025-07-14 | 5070736 | 9016536 | Red | Red | Red | Green | Green | Delivery of ESIP Platform to DJCS in July 2025 remains on track. The planned delivery cost of $5,070,736 reflects the expected cost of the project prior to the transition to DJCS. The revised delivery cost has been amended to $9,016,536 to account for the re-baselined project schedule and enhanced scope for the transition of the platform to DJCS. The increase in delivery cost remains within the original overall approved program funding budget.
Q4 24-25 | Royal Women’s Hospital | RWH | 3703 | Rostering, Time and Attendance Project | Health | Human Capital / Workforce Management | The Project will upgrade the current Rostering system, delivering performance improvements and new enhanced functionalities. This project is part of an overarching People Systems Improvement Program with Royal Melbourne Hospital and Western Health | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-07-03 | 2023-09-01 |  | 2023-09-01 | 31980 |  | 2023-09-03 |  | 2024-12-31 | 2025-10-30 | 1140573 |  | Green | Amber | Green | Green | Amber | The project is currently rated Amber due to a budget overrun from the extended timeline and the risk of potential delays if issues are identified during testing. Funding option discussions are progressing, and measures are being implemented to manage the associated risks.
Q4 24-25 | Royal Women’s Hospital | RWH | 3719 | Business Intelligence & Analytics Replacement System (BIARS) | Health | Business Intelligence | Business Intelligence (BI) and analytics upgrade for infrastructure and software by partnering with external provider. Decommission current BI system (RISE) and provide better system capability for operational reporting requirements. | Closed - Completed | Cost Reduction (Financial) | 2025-04-07 | PRINCE2 | 2023-05-01 | 2023-06-01 |  | 2023-06-01 | 100000 |  | 2023-12-04 |  | 2024-11-30 | 2025-04-07 | 2671976 |  | Green | Amber | Amber | Green | Green | Go-live occurred for Finance and Clinical dashboards occurred Monday April 7. Project has been marked as completed/closed.
Q4 24-25 | Austin Health | AH | 3721 | Austin Health Financial Management Information System | Health | Financial Management | The Financial Management Information System will replace an end of life system, introducing efficiencies and continuation of financial & supply chain management at Austin Health. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-06-30 | PRINCE2 | 2023-04-03 | 2024-02-28 |  | 2024-02-28 | 0 |  | 2024-03-18 |  | 2025-03-03 | 2025-06-30 | 11414550 |  | Green | Amber | Amber | Green | Green | Go Live April 1st. Complete Hypercare. Additional End-User Training. Project closed.
Q4 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 3722 | Mosaiq Migration to Cloud and Upgrade | Health | Systems Management | The Mosaiq Migration to Cloud and Upgrade project will move the Mosaiq Radiation Therapy Treatment System from on premisses to Azure Cloud and upgrade its version once in cloud, as current software version is becoming end of life. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2022-03-01 | 2023-12-22 | 2024-04-30 | 2024-04-30 | 0 | 20475 | 2024-05-01 |  | 2025-08-31 |  | 1720000 |  | Green | Green | Green | Green | Green | Project tracking in accordance to plan. Activities for database and user environment readiness are underway.
Q4 24-25 | Department of Health | DH | 3731 | Managed Services Provider Replacement (MSPR) | Health | Data Management,Development and Integration | Replacement of the Managed Service Provider (MSP) for the Applications and Services (AS) business unit within the Digital Health branch of the Commissioning and System Improvement division. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-06-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-12-31 | 2026-05-31 | 1412500 | 1422000 | Green | Amber | Amber | Red | Amber | Project is Amber due to procurement delay which is impacting schedule.
Q4 24-25 | Essential Services Commission | ESC | 3732 | Victorian Energy Upgrades (VEU) IT System Upgrade | Environment and Water | Analyses and Statistics ,Customer Relationship Management,Development and Integration | The project will deliver a replacement to the existing VEU registry system to improve information access, process management and consumer engagement, meeting new legislative and regulatory requirements. | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-06-03 | Agile | 2023-08-01 | 2024-08-30 | 2024-03-28 | 2024-03-28 | 500000 |  | 2024-03-28 |  | 2025-01-24 | 2025-06-02 | 7709000 | 10451065 | Green | Amber | Green | Green | Green | The system was delivered and fully operational on the planned go-live date of 2nd June 2025.
Q4 24-25 | Department of Health | DH | 3733 | St Vincent's Electronic Medical Record Project | Health | Analyses and Statistics ,Collaboration ,Communication,Forms Management,Organisational Management ,Records Management | Implementation of an electronic medical record (EMR) to streamline clinical documentation medication management and other clinical activities to support the provision of safer higher quality and more efficient patient care. | Initiated |  |  | PRINCE2 | 2023-09-01 | 2024-07-01 | 2025-10-01 |  | 0 | 3000000 | [11 empty] | The St Vincent's Hospital Melbourne Electronic Medical Record (EMR) project has transitioned to the preparatory phase to support organisational readiness for formal project commencement. The technical readiness program continues which includes an organisation-wide technology audit, completion of an Implementation Planning Study (IPS) for an enterprise billing solution and the significant progress of network readiness. An EMR team has been onboarded to support the preparatory works for the program.
Q4 24-25 | Melbourne Water | MELB Water | 3734 | Finance System Cloud Transition | Environment and Water | Financial Management | Due to a vendor decision to move all on-premise customers to SaaS by 2024 this project is required to upgrade Melbourne Waters finance system and move to the cloud. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2023-07-03 | 2024-01-24 | 2024-05-02 | 2024-05-02 | 0 |  | 2024-05-02 |  | 2024-12-17 | 2025-09-15 | 1811601 | 2439186 | Green | Amber | Green | Green | Green | As at 20250630: Change request approval to realign budget and timelines to the new go live window expected by the business for Q1 FY25/26. The new go live date is to ensure the finance system was not undergoing major change during end of financial year.
Q4 24-25 | Lower Murray Urban and Rural Water Corporation | LMUR Water | 3749 | Technology Uplift Program (Formerly - Business Transformation Program) | Environment and Water | Customer Relationship Management,Data Management,Financial Management,Human Capital / Workforce Management ,Human Resources,Reporting ,Supply Chain Management | Enabling LMW of the Future. The program will uplift capabilities across key business functions, including customer service, billing, assets and workforce and financial management to enable improved customer service and efficiency.​ | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2024-02-02 | 2024-05-30 | 2024-05-31 | 899582 |  | 2024-06-03 |  | 2026-06-30 |  | 12100105 |  |  | Green | Green | Green | Green | Scheduled activities are proceeding as planned with minimal/no impacts for this quarter.
Q4 24-25 | Department of Families, Fairness and Housing | DFFH | 3756 | Communities and Families Transformation - Stage 1 | Community Services | Customer Relationship Management | Deliver a business case with options for strategic investment in technology platforms, underpinning delivery of care services to communities and families, to enable seamless interactions and experience for our clients and sector partners. | Delivery | Social Improvement (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-08-15 | 2024-01-11 | 2023-01-11 | 2023-06-19 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2025-12-19 | 14429000 |  | Green | Green | Green | Green | Green | Project progressing to cost and revised schedule.
Q4 24-25 | Department of Transport and Planning | DTP | 3757 | Human Capital Management (HCM) Project - Phase 2 | Transport and Vehicles | Business Intelligence,Customer Initiated Assistance,Forms Management,Management of Process ,Tracking and Workflow | To lead the implementation of SAP SuccessFactors (including Payroll) for DTP . Program scope includes the changes required for the Machinery of Government (MoG) changes announced in December 2022. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-01 | 2023-06-30 |  | 2023-08-14 | 0 |  | 2023-08-14 |  | 2024-06-30 | 2025-06-30 | 7490000 | 10440751 | Amber | Green | Amber | Amber | Amber | The overall status is amber from the baseline of the scope schedule and budget. There is continued pressure on the schedule due to delays with workstreams and an increasingly complex operating environment. The project team is working with the steering committee to resolve the issues and will inform the revised delivery end date in the next reporting period.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 3761 | Marine Search and Rescue Radio Replacement | Emergencies and Safety | Communication | The project will connect Marine Search and Rescue units to the Victorian Radio Network and provide 7 base radios, 32 mobile radios and 130 portable radios. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-06-30 | Project Management Excellence | 2023-01-01 | 2023-01-10 |  | 2023-01-10 | 0 |  | 2023-03-01 | 2023-01-11 | 2024-12-01 | 2025-06-30 | 1377000 | 2141072 | Green | Green | Green | Green | Green | The project is complete. The scope was delivered within schedule and budget.
Q4 24-25 | Yarra Valley Water | YV Water | 3762 | Enterprise Analytics Platform - Phase 2 | Environment and Water | Data Management | Replacement of YVW's data warehouse, operational data-store and business intelligence reporting technologies with a modern, scalable data and analytics platform | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2023-09-01 | 2023-09-30 |  | 2023-09-30 | 0 |  | 2023-10-01 |  | 2025-04-28 | 2026-06-30 | 6640340 | 8243140 | Amber | Amber | Amber | Amber | Amber | Reporting Amber due to significant schedule delays. Decision to terminate vendor contract and assess options for remaining deliverables, to be presented in July to exec.
Q4 24-25 | State Revenue Office | SRO | 3765 | Payroll tax Reform | Government and Economy | Development and Integration | Implement system changes to administer payroll tax changes introduced in the 2023 Victorian Budget – temporary COVID surcharge, removing private school exemptions and the sliding scale deduction – as well as GP changes introduced in May 2024. | Closed - Completed | Customer Satisfaction (Non Financial), Increased Revenue (Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-05-23 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-03 |  | 2025-06-30 |  | 4772200 | 4462070 | Green | Green | Green | Green | Green | The project has been completed, meeting the expected scope, schedule and budget.
Q4 24-25 | Melbourne Polytechnic | MelbPoly | 3767 | Melbourne Polytechnic Student Management System Implementation | Employment, Skills and Workplace | Systems Management | Selection and Implementation of new Student Management System for Melbourne Polytechnic to improve student and user experience, increase digitalisation and automation, and improve functionality and compliance. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-29 | 2023-12-31 |  | 2024-01-08 | 182000 |  | 2024-01-15 |  | 2027-01-29 |  | 7818000 |  | Green | Green | Green | Green | Green | Project progressing as per plan and targets.
Q4 24-25 | Department of Transport and Planning | DTP | 3773 | Future Public Transport Ticketing System | Transport and Vehicles | Customer Initiated Assistance,Customer Preferences,Financial Management,Systems Management | The future Public Transport Ticketing (PTT) System will deliver modern customer payment features and progressively replace the current myki Ticketing System (myki System) | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2020-07-01 | 2021-10-18 |  | 2021-10-18 | 0 |  | 2021-10-18 |  | 2028-06-30 | 2028-12-31 | 543000000 | 680350000 | Green | Green | Green | Green | Green | The program is reporting an overall status as green. The program implementation activities are ongoing.
Q4 24-25 | Environment Protection Authority | EPA | 3781 | MAJ128 - Website and intranet refresh | Environment and Water | Collaboration ,Communication,Content Management | Improving EPA’s internal and external channels (website, intranet and reporting tools) to improve user experience and awareness | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-06-30 | Hybrid - Agile and Waterfall | 2023-05-11 | 2023-12-31 | 2023-08-15 | 2023-08-15 | 0 |  | 2023-08-16 |  | 2024-06-28 | 2025-06-30 | 2666000 | 3930147 | Amber | Red | Amber | Amber | Green | The website has been successfully launched and the Project Closure Report is currently in development.
Q4 24-25 | Box Hill Institute Group | BHIG | 3786 | Campus Network Infrastructure Upgrade | Employment, Skills and Workplace | Systems Management | Replacement of network infrastructure hardware and software assets within data centres and across all campuses that do not meet the minimum operational requirements related to supportability capacity performance reliability and security. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2023-08-01 | 2023-12-22 |  | 2023-12-22 | 129131 |  | 2023-12-22 |  | 2025-02-28 | 2025-09-30 | 6860000 |  | Amber | Red | Green | Amber | Green | Most activities planned were completed successfully and on time. The small amount of outstanding work in the period was caused by additional network infrastructure not delivered in timeframes needed. However this infrastructure has now arrived and deployment will occur in early Q1 2025/26. This delay has no effect on overall schedule. The high risk and critically important upgrades to both data centre networks were completed successfully. All remaining cabling for and installation of new wireless access points across Lilydale and City campuses was completed on time.
Q4 24-25 | Court Services Victoria | CSV | 3794 | Wyndham Law Courts - Technology Component | Law and Justice | Assets/Materials Management,Development and Integration | This objective of the project requires the preparation of the new Wyndham site to be a member of the Cenitex GSP INTERNAL network for initial use by Customers and Court staff. | Closed - Completed | Customer Satisfaction (Non Financial) | 2025-06-30 | Hybrid - Waterfall and Agile | 2023-12-20 | 2024-03-29 |  | 2024-06-03 | 0 | 0 | 2024-06-03 |  | 2025-03-31 | 2025-06-30 | 1330000 | 1333849 | Green | Green | Green | Green | Green | Project is now complete.
Q4 24-25 | Victorian Electoral Commission | VEC | 3802 | Roll Managment System (RMS) Technical Upgrade | Government and Economy | Systems Management | The project will replace the legacy RMS application with a new and supported technology platform, reducing VEC's risk of using an unsupported platform and enabling system continuity for roll management | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-04-14 | 2023-11-08 |  | 2023-11-10 | 880742 |  | 2023-11-10 |  | 2025-09-30 | 2025-10-24 | 7841489 | 8456690 | Green | Green | Amber | Amber | Amber | The project remains at 'Amber' status tracking with a minor slippage in the schedule necessitated to ensure a quality outcome is delivered but remaining within an acceptable tolerance. Implementation planning and associated activities have commenced.
Q4 24-25 | Melbourne Water | MELB Water | 3807 | Network Resilience FY25-26 | Environment and Water | Assets/Materials Management | To continue investing in our IT network ensuring that we reduce the risk of unplanned network outages meet compliance requirements improve our security posture increase capacity reliability and bandwidth to accommodate future growth. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | PMBoK | 2023-12-08 | 2024-02-27 |  | 2024-07-24 | 0 |  | 2024-07-24 | 2024-10-22 | 2026-06-22 | 2026-10-26 | 4966804 | 5216808 |  | Green | Green | Green | Red | As at 20250630: Identified a change of scope need to provide for additional support requirements, resources and related increase in budget needs. A project change request to be submitted Q1 FY25/26 and is still on schedule.
Q4 24-25 | Melbourne Water | MELB Water | 3808 | Virtualised Software and Server Upgrades | Environment and Water | Systems Management | Project is to upgrade the current version of Virtual software due to end-of-life support and upgrade servers. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-05-21 | PMBoK | 2023-11-29 | 2024-04-01 |  | 2024-05-31 | 0 |  | 2024-05-31 |  | 2025-04-07 |  | 1842537 |  | Green | Green | Green | Green | Green | Project is complete.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 3811 | Contact Centre Capability Uplift | Employment, Skills and Workplace | Communication | WorkSafe’s telephony system is built upon ageing infrastructure and tech. The introduction of a contact-centre-as-a-service will uplift person-centred services and ensure continuity for frontline support of injured workers and the Victorian community | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2022-01-01 | 2023-11-26 |  | 2023-12-11 | 441569 | 326274 | 2023-12-11 |  | 2025-12-31 |  | 7321441 | 3867488 | Green | Green | Green | Green | Green | On track
Q4 24-25 | Grampians Rural Health Alliance | GRHA | 3812 | Grampian Health - Electronic Medical Record System | Health | Data Management | Implementation of an Electronic Medical Record system across five campuses of Grampians Health, namely Ballarat, Dimboola, Edenhope, Horsham, and Stawell. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-31 | 2028-06-30 | 2025-10-31 |  | 0 | [12 empty] | Grampians Health continues to progress a shared EMR program with another Victorian health service. Procurement is in progress but has taken longer than anticipated and is expected to push out program timelines by approximately 12 months, delivery expected to commence in Q4.
Q4 24-25 | Ambulance Victoria | AVS | 3815 | VACIS Modernisation Device Pilot | Health | Data Management | The project will pilot new Patient Care Record devices for paramedics to reduce administrative time, and improve information access and response performance, enabling paramedics to make timely decisions when treating patients. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-12-01 | 2023-06-30 |  | 2023-07-01 | 700000 | 700000 | 2023-07-27 |  | 2024-12-31 | 2025-06-30 | 3215813 | 2380872 | Amber | Amber | Red | Green | Green | The program is not completed and transitioned to BaU.
Q4 24-25 | Ambulance Victoria | AVS | 3816 | Rostering System Replacement (WMS) | Health | Systems Management | The project will replace the current end-of-life rostering software with a new workforce management solution, minimising software stability and security risks, and improving efficiency in rostering processes to deliver more impact to our community. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-30 |  | 2024-03-31 | 1271134 | 826551 | 2024-04-01 |  | 2025-06-30 | 2025-10-30 | 3846467 | 6370186 | Amber | Amber | Amber | Amber | Amber | 'The project is tracking Amber because of risks and issues associated with vendor resourcing mobilsation challenges. The project team will continue to manage closely during Q1 FY26.
Q4 24-25 | Royal Victorian Eye and Ear Hospital | Eye & Ear | 3817 | Electronic Referrals | Health | Communication,Customer Relationship Management,Document Management | The eReferral project will implement digital referral processes delivering improved efficiency, more effective prioritisation of urgent referrals, to provide shorter turnaround times for patients and improved provider communication. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-05-30 | Waterfall | 2022-06-01 | 2022-10-31 |  | 2022-11-10 | 0 |  | 2023-07-03 |  | 2024-12-31 | 2025-05-30 | 1240000 |  | Amber | Amber | Amber | Green | Green | The eReferral project has successfully concluded with the system go-live in May.
Q4 24-25 | Ports Victoria | PortsVic | 3824 | Port Management Information System (PMIS) Project | Transport and Vehicles | Routing and Scheduling | Implementation of a Port Management Information System (PMIS), directly supporting the management of maritime navigation and operational safety, providing safe, fair, and efficient access for the commercial ports of Melbourne, Geelong and Hastings. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-20 | 2025-08-31 |  | 0 | 0 | [11 empty] | The project experienced minor delays throughout its procurement phase and tender evaluation activities. The formal tender evaluation activities will be completed in end July, with the project team seeking governance approval for contract award and execution by end August. Subject to approval, the project will commence delivery activities with the successful contractor in September. Tracking updates will be provided in the next reporting period.
Q4 24-25 | Chisholm Institute of TAFE | Chisholm TAFE | 3825 | Chisholm Student Management System Transformation Project | Employment, Skills and Workplace | Records Management | The project will migrate legacy student management system to new technology offered by the existing vendor to minimize technology risk and maintain student experience and business continuity. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-09 | 2023-05-31 |  | 2023-05-31 | 0 |  | 2023-11-16 |  | 2026-09-25 | 2027-12-31 | 8000000 |  | Green | Amber | Amber | Amber | Green | The project plan is re-aligned due to the complexity of the functionality being designed and built. The proposed revision has been approved by the governance committee with no impact to the $8M delivery budget.
Q4 24-25 | Department of Transport and Planning | DTP | 3828 | Trusted and Secure Program | Transport and Vehicles | Data Management,Security Management ,Systems Management | The objective of this program is to implement cyber and information security standards, enhancing information security measures and reducing risks of cyber incidents, by embedding robust and proactive cyber security practices. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-01 | 2023-10-02 |  | 2023-10-02 | 0 |  | 2023-10-03 |  | 2024-06-30 | 2026-06-30 | 6800000 | 17356852 | Green | Green | Green | Green | Amber | The program status is reported as amber. The status is amber due to the challenges related to project workstreams. The program team is working on mitigating these risks. The program includes thirteen completed project streams with seven others in progress.
Q4 24-25 | Department of Transport and Planning | DTP | 3829 | Public Transport Data program (PTDP) (Formerly known as ITDP) | Transport and Vehicles | Business Intelligence,Communication,Customer Initiated Assistance,Customer Preferences,Data Management,Search | Purpose of this program is to improve the Department’s capability to deliver accurate and consistent real-time information for customers whenever, wherever and however they need it. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-03-29 | 2023-08-31 | 2023-08-31 | 0 | 0 | 2023-09-01 | 2024-01-01 | 2025-11-30 |  | 16140000 |  |  |  |  | Amber | Amber | The program status is amber due to the solution implementation issues and dependencies with other workstreams. The mitigation is for the program team to work closely with the workstreams and the broader organisation to develop options for consideration by the project control board.
Q4 24-25 | HealthShare Victoria | HealthShare | 3835 | Healthshare Victoria Long Term Warehouse Management System Solution | Health | Supply Chain Management | The implementation of a scalable Warehouse Management System to support Healthshare Victoria's current & future growth plans, enabling a safer, effective and efficient distribution centre operations | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2022-12-05 | 2023-09-05 |  | 2023-09-06 | 0 |  | 2023-09-07 |  | 2025-01-31 | 2025-08-31 | 6218693 |  | Amber | Amber | Amber | Green | Green | The overall project status is green as key issues were resolved and WMS is deployed in both DC’s (Derrimut and Dandenong) as per the plan. Hypercare extended due to vendor delays in handing documentation over to BAU support and agreeing processes
Q4 24-25 | Austin Health | AH | 3837 | CRM Statewide Project | Health | Customer Relationship Management | Make five CRM modules available to all metropolitan and some regional health agencies, improving referral management and waitlist management, providing efficiencies and improved waiting lists. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-02 |  | 2024-12-31 | 2026-06-30 | 4565000 | 9509070 | Amber | Amber | Green | Green | Green | - Deployed Module 1 at Bendigo scheduled at Western and Ballarat. Albury build completed - Deploying Module 2 at Eastern and Mercy Health - Robot Process Automation POC completed - Deployment schedule filled until end of project period
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3839 | Biosciences Advanced Scientific Computing (BASC) Infrastructure Refresh Project | Government and Economy | Knowledge Discovery | The BASC Infrastructure Refresh project will deliver refreshed infrastructure to replace an end-of-life system that supports agricultural research. This project will be delivered in three phases over the next three years. | Delivery | Compliance (Non Financial), Cost Reduction (Financial), Eco Improvement (Non Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-25 | 2024-06-28 | 2024-12-31 | 2024-12-31 | 150000 | 399415 | 2025-01-01 |  | 2027-12-18 |  | 3675686 | 4054654 |  |  |  | Amber | Amber | The project reported an Amber status due to a few remaining activities in Phase 1 delaying the schedule. The vendor is working to recover these delays by next quarter. Note that the project budget reflects the Phase 1 budget only and will be incrementally adjusted based on the subsequent phase planned commitment.
Q4 24-25 | Barwon Region Water Corporation | BR Water | 3841 | C1430 - Network Segmentation | Environment and Water | Security Management | The Network Segmentation project will segregate and segment the operational and corporate networks reducing the impact and recovery time of a network security breach ensuring the reduction in cyber incident risk profile and improved SOCI compliance. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-02-01 | 2023-04-14 |  | 2023-04-14 | 15000 |  | 2023-04-14 |  | 2024-11-07 | 2026-08-31 | 1477000 | 2983000 | Red | Red | Green | Green | Green | Project is tracking on budget and schedule against the baseline set by the project change request (approved Nov 2024).
Q4 24-25 | Barwon Region Water Corporation | BR Water | 3842 | C1443 - Land Development and New Connections Transformation | Environment and Water | Customer Relationship Management | The Land Development and New Connections Transformation project will redesign and configure services delivered by the Land Development and Connections functions increasing innovation, reliability and customer affordability. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Waterfall | 2021-11-01 | 2022-10-31 |  | 2022-10-31 | 75000 |  | 2022-11-07 |  | 2024-09-30 | 2025-07-31 | 1414000 | 1341000 | Green | Amber | Amber | Red | Red | All development work has been completed. Further activities will be focused on testing and ensuring a smooth rollout of the remaining scope with a forecasted end date of 31 JUL 2025.
Q4 24-25 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3843 | Human Resources Information System Replacement | Education | Human Resources | Replace BKI’s ageing HR and Payroll systems with a modern cloud-based platform which will enable improved HR processes, improved user experience and significantly improved people data and reporting. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-01 | 2023-12-08 |  | 2023-12-08 | 370000 | 125000 | 2024-02-01 |  | 2025-03-31 | 2025-12-19 | 2643965 | 2888965 | Green | Amber | Amber | Red | Red | Phase 2 go-live has been delayed due to significant risks arising from ongoing Enterprise Agreement negotiations and potential backpay obligations which have necessitated a pause in deployment; in addition missed requirements in the payroll module from the initial build are currently being addressed to ensure full functionality and compliance. A revised Phase 2 go-live date will be confirmed once the final Enterprise Agreement has been signed and key remediation activities are complete.
Q4 24-25 | Department of Health | DH | 3844 | Security Access Modernisation | Health | Systems Management | Cloud application migration from legacy TAM6 to ISVA10 environment, and engagement with business teams to transition their onboarding process to use Departmental User Onboarding Portal V2, reducing operational risk of the unsupported TAM6 platform. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-06-28 |  | 2024-06-28 | 574077 |  | 2024-06-28 |  | 2025-06-30 | 2025-12-31 | 1413388 | 1387986 | Green | Green | Green | Amber | Green | Project is progressing to revised schedule and cost.
Q4 24-25 | Bendigo Kangan Institute of TAFE | BKI TAFE | 3845 | Apprentice and Trainee Management Module Implementation | Education | Systems Management | This project will deliver functionality into the core student management system to be enable apprentice and trainee student management. This will bring all BKI students management onto one platform, reducing integration and data risks | Postponed | Increased Revenue (Financial) | 2025-06-05 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-30 | 2023-12-08 |  | 2023-12-08 | 200000 |  | 2024-01-08 |  | 2025-06-30 | 2025-12-31 | 3157730 | 4311828 | Green | Red | Red | Red | Red | With further build delays impacting go-live, a strategic pause and 90 day re-plan decision was reached by Senior Executive on 5th June
Q4 24-25 | Department of Health | DH | 3846 | SDWAN activities and production rollout | Health | Systems Management | Delivering a new resilient, secure and internet centric network solution to all Department of Health and Families, Fairness and Housing sites, supporting the departments move towards cloud based IT services. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2023-12-01 |  | 2023-12-04 | 0 |  | 2024-01-02 |  | 2025-06-30 | 2025-12-31 | 1422000 | 1835326 | Green | Green | Green | Green | Green | Project progressing to revised cost and schedule.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 3849 | Self Insurance Uplifting Oversight of Claims Management Performance | Employment, Skills and Workplace | Business Intelligence | The Self-Insurance (SI) Uplifting Oversight project aims to develop and implement a solution for receiving additional (transactional level) electronic data from Self-Insurer’s (SI’s) more frequently (monthly) and enhance oversight and performance. | Closed - Completed | Compliance (Non Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | PRINCE2 | 2021-01-08 | 2022-06-30 |  | 2022-09-06 | 0 |  | 2022-12-06 |  | 2025-06-30 |  | 2669306 | 3652379 | Green | Green | Green | Amber | Green | Project closed
Q4 24-25 | Western Health | WH | 3851 | Western Health - Mental Health Transition (ICT Infrastructure) | Health | Development and Integration | WH and RMH teams are migrating IT services to WH. Priority is minimal disruption to services, with workarounds in place to maintain service continuity and direct access to the Project team to address any issues potentially impacting patient care. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2023-07-01 | 2023-10-30 |  | 2023-11-20 | 0 |  | 2024-01-01 |  | 2024-10-30 | 2025-08-29 | 1960000 |  | Green | Green | Green | Amber | Green | Delivery of end user devices completed in June. Transition of IT services for staff to be completed in Q1 25/26 reporting period
Q4 24-25 | Workplace Injury Commission | WIC | 3853 | Case Management System | Law and Justice | Tracking and Workflow | Implementation of a new case management system that improves efficiency and productivity, to support the resolution of workplace injury disputes for Victorian workers. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-14 | 2024-10-30 | 2025-08-29 |  | 0 | 2500000 | [11 empty] | Following issuing of an RFP vendor evaluation is underway with the aim to select/appoint a preferred vendor in the coming months
Q4 24-25 | Department of Justice and Community Safety | DJCS | 3854 | Impact Assessment Strategic Project | Emergencies and Safety | Data Management | This project will deliver improvements to Impact Assessment processes and systems in Victoria, aiming to provide efficient, timely and appropriate support for communities impacted by an emergency. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Project Management Excellence | 2023-08-01 | 2024-01-31 |  | 2024-01-31 | 255242 |  | 2024-02-01 |  | 2025-06-30 | 2025-12-31 | 6800000 |  | Green | Green | Green | Amber | Green | The project is tracking well against scope, budget and schedule.
Q4 24-25 | Department of Health | DH | 3856 | Mental Health and Wellbeing Client Management System Implementation Project (MHWCMS) | Health | Data Management,Development and Integration | Delivery of a Mental Health and Wellbeing Client Management System to the Mental Health Sector to replace CMI/ODS and acquit recommendation 62 in the Royal Commission into Victoria’s Mental Health System. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2023-12-01 | 2023-12-22 |  | 2023-12-22 | 0 |  | 2024-01-01 |  | 2026-06-30 | 2028-06-30 | 40229527 | 64700000 | Green | Green | Amber | Red | Red | Project status is Red due to constraints in accessing required services and procurement delays impacting schedule. This issue has been escalated to executive stakeholders. The project team continues to progress technical readiness activities and planning for mental health and wellbeing local services deployment.
Q4 24-25 | Department of Education | DE | 3857 | ARC 4.0 (Expansion and Enhancement - Lessons Plans) | Education | Content Management,Management of Process | To empower educators and learners by creating a comprehensive and user-friendly lesson plan management system within the Arc. This system will streamline lesson planning enhance learning experiences and improve learning outcomes. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-06-30 | Agile | 2024-02-19 | 2024-02-19 |  | 2024-02-19 | 91318 |  | 2024-03-20 |  | 2024-07-26 | 2025-06-30 | 1034685 | 2609682 | Green | Amber | Amber | Amber | Green | The project has successfully delivered the initial technology components for the Victorian Lesson Plans and is now closed.
Q4 24-25 | North East Link State Tolling Corporation | NELSTC | 3858 | Toll Collection Capability (TCC) - Roadside Systems (RSS) | Transport and Vehicles | Analyses and Statistics ,Communication,Data Management,Development and Integration ,Records Management ,Reporting | The Roadside Systems will effectively & efficiently detect vehicles and capture tag or vehicle details ensuring toll revenue is collected accurately and road users have a seamless experience while accessing North East Link. | Initiated |  |  | PMBoK | 2023-06-27 | 2025-09-26 | 2026-06-29 |  | 1117000 | [12 empty] | The TCC RSS contract was awarded in FYQ4 25 and now in the delivery phase. The project is progressing to plan and approved budget with an overall green rating. The project will remain in initiation until TCC - Back Office Systems (BOS) procurement completes in FY26 Q4 to maintain procurement integrity. The TCC RSS and TCC BOS projects are complementary streams of the one project which share a budget. Disclosing the full cost of TCC RSS could potentially enable TCC BOS respondents to derive the BOS budget compromising procurement integrity and competitive positioning. The Revised Initiation End Date reflects this approach.
Q4 24-25 | North East Link State Tolling Corporation | NELSTC | 3859 | Toll Collection Capability (TCC) - Back Office Systems (BOS) | Transport and Vehicles | Communication,Customer Initiated Assistance,Customer Relationship Management,Management of Process ,Reporting | The Back Office Systems will efficiently manage trip formation, interoperability between Australian Toll Roads, billing and collection of toll revenue while providing road users an efficient way to pay for their travel on North East Link. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-27 | 2026-06-29 |  |  | 1117000 | [12 empty] | The project will remain in initiation until procurement completes in FY26 Q4 to maintain procurement integrity. Governance approvals to proceed to the BOS RFP were received. The BOS RFP is in progress and progressing to baseline schedule and within the approved budget.
Q4 24-25 | Coliban Region Water Corporation | Coliban Water | 3860 | Core Capability Uplift | Environment and Water | Financial Management | New software implementation and business processes optimisation to uplift the Commercial and Financial Management capabilities, directly contributing to the strategic goals of ‘Financial Sustainability’ and ‘An Adaptive and Resilient Organisation’. | Initiated |  |  | PMBoK | 2023-08-08 | 2024-07-02 | 2025-07-02 |  | 0 | [12 empty] | “The project is tracking well against scope, budget and schedule for its stage. The project procurement phase is complete and the contract to deliver has been awarded. Project kick-off is scheduled for early Q1 2025-2026.
Q4 24-25 | Department of Education | DE | 3862 | Victorian Curriculum and Assessment Authority (VCAA) Student Portal | Education | Communication,Customer Initiated Assistance,Reporting ,Tracking and Workflow | The student portal will provide a new digital channel for senior secondary students to access a range of VCAA services including enrolment details examination timetables and academic records, reducing reliance on paper records. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Agile | 2023-07-03 | 2023-11-30 |  | 2023-11-30 | 20000 |  | 2024-02-26 |  | 2025-03-31 | 2025-07-21 | 2405203 | 3033573 | Amber | Green | Green | Green | Green | The project has successfully delivered the technology component of the Victorian Curriculum and Assessment Authority (VCAA) Student Portal required for launch. Rollout and handover planning is well progressed with a potential staged implementation to occur as part of business operations.
Q4 24-25 | Greater Western Water Corporation | GW Water | 3863 | Asset, Works & Field Services Mgmt Consolidation (Concordia) | Environment and Water | Assets/Materials Management,Collaboration ,Data Management,Development and Integration ,Human Capital / Workforce Management ,Reporting ,Systems Management | AWFSMC serves as a foundational pillar to transform future ready Field Service mgmt & Asset & Works Mgmt capabilities . It will increase business & customer satisfaction & will be delivered in phases with budget increases reflecting each phase | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2023-09-11 |  | 2023-09-11 | 760490 |  | 2023-09-11 |  | 2028-06-30 | 2026-06-30 | 3436310 | 8470976 | Green | Green | Green | Amber | Green | Project has successfully completed 20 Asset system deployments in FY25 along with asset register consolidation of former Western Water and City West Water data. Project continues to deliver against agreed scope to enhance capabilities with the focus next quarter on delivering field services inventory solution. NOTE: Reported delivery costs reflect the current phase of the project. Each phase will provide further clarity on cost.
Q4 24-25 | Greater Western Water Corporation | GW Water | 3864 | Geospatial Capability Uplift (OSO 2030) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Data Management,Visualisation | The project will enhance geospatial capability through modern standards and technologies to maximise value of spatial information in order to gain new insights for improved asset management capabilities across the organisation. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial) |  | Waterfall | 2023-07-01 | 2024-04-07 |  | 2024-04-07 | 3900000 |  | 2024-04-07 |  | 2028-06-30 |  | 20300000 |  | Amber | Green | Green | Green | Green | Continuation of agreed scope in Q4 including phase 1 of data migration activities.
Q4 24-25 | Department of Justice and Community Safety | DJCS | 3869 | Replacement DJCS Safety Incident Management System | Community Services | Reporting | Procurement, and implementation of a safety incident management system will streamline how safety incidents are reported and investigated. This system will foster a proactive safety culture where incidents are managed efficiently and effectively. | Postponed |  | 2025-06-30 | Project Management Excellence | 2023-12-19 | 2024-01-31 | 2024-01-04 |  | 0 | [5 empty] | 0 | [6 empty] | The project has been approved to commence procurement activities for the provision of a safety incident management system. External market research is complete, however due to resourcing constraints, the project has been postponed until project resources are available to carry out procurement activities.
Q4 24-25 | Holmesglen Institute of TAFE | Holmesglen TAFE | 3870 | Identity Governance and Administration | Employment, Skills and Workplace | Security Management | The IGA project will deliver a new Identity Governance & Administration platform. The new IGA platform will improve staff/student identity governance and security by enabling contemporary features such as attestation and hardened authentication. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-09-14 | 2023-11-15 |  | 2023-12-06 | 0 |  | 2024-03-01 |  | 2025-03-28 | 2026-07-31 | 1205132 |  | Green | Green | Green | Green | Amber | Reviewing the project with newly established PMO. Functional and technical requirements are being re-evaluated based on discovery and testing with the student management system. Project timelines will be re-baselined based on PMO findings. Timelines will be confirmed in the next quarter.
Q4 24-25 | Austin Health | AH | 3877 | Anesthetics & Device Integration (AnDI) Project | Health | Development and Integration ,Document Management ,Knowledge Management ,Management of Process | Digitising theatre based documentation and integrating monitoring device data into the Electronic Medical Record, for safer patient outcomes and improved efficiency. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Agile | 2024-05-27 | 2024-08-05 |  | 2024-08-05 | 0 |  | 2024-08-05 |  | 2025-08-29 |  | 4585000 |  |  | Green | Green | Green | Green | Complete cabling for device integration. Complete end user education. Phase 1 and 2 go live in May. Commence analysis of optimisations.
Q4 24-25 | South East Water | SE Water | 3879 | Sample Management | Environment and Water | Assets/Materials Management,Management of Process | The project will deliver a sample management system to streamline current processes, modernising the system capability, and enabling improved reporting, faster processes and insights for customer water quality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-04-08 | 2024-08-01 |  | 2024-08-01 | 159445 |  | 2024-09-02 |  | 2025-07-31 | 2026-06-30 | 1937205 |  |  | Green | Green | Green | Green | Successful delivery of Phase 1 completed in Q4 without major issue. Project has now kicked off discovery and detailed planning for Phase 2.
Q4 24-25 | Northern Health | NH | 3880 | Active Directory Segregation from Melbourne Health | Health | Systems Management | Northern and Melbourne Health are currently sharing the same Active Directory. Segregating from this shared active directory to a more modern version will allow NH to initiate its journey into cloud and enhance cyber security across all campuses | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2022-01-01 | 2022-09-27 |  | 2022-09-27 | 0 |  | 2023-03-09 |  | 2025-09-30 |  | 3200000 |  | Amber | Green | Green | Green | Amber | Complications in the build of the new Citrix environment are pushing the project to an amber status. These challenges are being addressed as a priority to ensure a timely resolution is provided.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 3881 | Medical Panels Capability Uplift | Employment, Skills and Workplace | Tracking and Workflow | Medical Panels technology will migrate to a modern system enabling digital record-keeping, workflow automation, and improved cyber security. This mitigates the risk of end-of-life tech, improves efficiency, and uplifts staff / stakeholder experience. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-03 | 2024-12-05 | 2025-02-24 | 2025-02-24 | 947722 | 758291 | 2025-02-25 |  | 2025-10-31 |  | 4999889 | 4914431 |  |  |  | Amber | Amber | Delivery is delayed due to a late start. Planning activities with the vendor have also uncovered potential scope and resource gaps as well as work scheduled during the IT freeze period. The project will reassess key impacts and re-baseline the Execute phase via a change request.
Q4 24-25 | Melbourne Water | MELB Water | 3882 | Business Process Optimisation 24-26 | Environment and Water | Systems Management | This project aims to optimise business processes and workflows using modern process management tool, improving process efficiency & reducing reliance on manual processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-06-13 | 2024-10-25 |  | 2024-11-14 | 0 |  | 2024-11-14 |  | 2026-07-21 |  | 2900000 |  |  |  | Green | Green | Green | As at 20250630: Development work is continuing on multiple streams. Budget is Amber due to Melbourne Water metrics and remains within the upper limit.
Q4 24-25 | Victorian Gambling and Casino Control Commission | VGCCC | 3883 | Compass - Gambling License System (GLS) replacement project - Release 1 | Law and Justice | Customer Relationship Management | A new regulatory system to replace the legacy license management system. The project will remediate and uplift VGCCC's ICT infrastructure, improving ICT capabilities and enabling effective, risk-based, and intelligence-led regulatory approach. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-04 | 2024-09-06 | 2024-08-30 | 2024-08-30 | 36000 |  | 2024-09-02 |  | 2025-08-01 | 2025-09-01 | 1500000 | 1757000 |  | Green | Green | Green | Green | The project is tracking well. The scope was expanded to include digitisation of additional forms. The build phase has been completed, and the testing and data migration phase has commenced. The project is on track for delivery in September 2025.
Q4 24-25 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3884 | SEC Retail Customer Billing System | Energy and Resources | Customer Relationship Management | This project is implementing a Customer Billing System that will enable SEC to launch an Energy Retail Business servicing electricity C&I Customers. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-05-21 | 2024-10-11 | 2024-10-18 | 2024-10-31 | 225000 | 258000 | 2024-10-31 |  | 2025-09-30 |  | 2780120 | 3125120 |  |  | Green | Green | Green | Project has delivered key functionality to the business and is currently in hypercare with the vendor.
Q4 24-25 | Grampians Rural Health Alliance | GRHA | 3886 | Grampians Health Success Factors Phase 2 | Health | Human Resources | Implementation of SAP SuccessFactors, including Employee Central Payroll, refactoring of Employee Central, Recruitment, Onboarding, and implementation of Performance & Goals. Phase 2 will deliver integration with rostering, finance and IT systems. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-13 | 2023-12-15 |  | 2023-12-15 | 0 |  | 2024-08-14 |  | 2025-09-26 | 2025-11-28 | 2905553 |  |  |  | Green | Green | Green | System Integration Testing commenced mid-May however due to complexities took significantly longer than originally planned resulting in timelines being pushed out. User Acceptance Testing (UAT) will run from mid-July to early-August. Post UAT the project team will run two periods of parallel payroll testing prior to cutover to production. Recruitment and Onboarding activities have been finalised however will not go live until November in line with other modules. Performance & Goals (PMGM) will go live independently to the other modules and is due to go live early August.
Q4 24-25 | Greyhound Racing Victoria | GRV | 3887 | Greyhound Whole of Life Tracking (GWOLT) | Business and Industry | Analyses and Statistics ,Business Intelligence,Customer Relationship Management,Management of Process | Digital Whole of Life Greyhound Tracking (DGT) involves the digitised data capture storage and retrieval to automate processes for tracking and recording the location and health of Victorian greyhounds throughout stages of their lives. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-08 | 2025-01-31 | 2025-03-23 | 2025-03-23 | 0 |  | 2025-03-24 |  | 2026-03-31 |  | 2920000 |  |  |  |  | Green | Green | Delivery of the IT system has commenced. Communications and education to industry and participants has also commenced. The project is tracking well against scope, budget and schedule.
Q4 24-25 | Department of Government Services | DGS | 3889 | Common Corporate Platform (CCP) - VicGov People - DGS/DPC/DTF Cluster | Government and Economy | Human Capital / Workforce Management | Onboarding the Departments of Government Services, Premier and Cabinet, and Treasury and Finance on a common human capital management platform (VicGov People) to drive efficiency and productivity, enhancing employee experience and corporate services | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-04 | 2024-06-28 | 2024-06-01 | 2024-06-25 | 0 |  | 2024-07-01 | 2024-07-01 | 2026-06-30 | 2025-12-01 | 25000000 |  |  |  | Green | Green | Amber | The project reported amber due to constraints on key resources and unexpected delays in the implementation of a key technical dependency. The project has allocated additional monitoring and reporting on its partner's delivery. Achievement in Q4 included the completion of build and user testing for over 10 critical deliverables, as well as Mock 1 data migration activities during this quarter.
Q4 24-25 | Yarra Valley Water | YV Water | 3891 | Altus PPM Tool Implementation | Environment and Water | Investment Management | Implementation of a PPM tool to centralise visibility of up-to-date program information, support consistency in the way projects get delivered, and provide insights on demand. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2021-08-01 | 2024-08-15 |  | 2024-08-26 | 421280 |  | 2024-09-02 |  | 2026-06-10 |  | 2947600 |  |  | Green | Green | Amber | Amber | Technical build is well progressed however business adoption will take longer than expected. A significant area of the business is going through a restructure which has impacted key business user availability. The effects of the restructure and the impact continue to be assessed, the likely consequence being a CR for schedule and costs
Q4 24-25 | Fire Rescue Victoria | FRV | 3893 | Asset Sustainment | Emergencies and Safety | Assets/Materials Management | This project aims to procure ICT equipment to replace components at end-of-life. This includes equipment such as network equipment and fire station switches and will ensure a safe ICT environment and ensure ongoing reliability. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | FRV Project Management Framework (PMF) | 2020-07-01 | 2020-10-05 |  | 2020-10-05 | 0 |  | 2022-02-14 |  | 2024-12-31 | 2026-06-30 | 7069087 | 6967773 | Green | Green | Green | Green | Green | The project is tracking well against scope, budget and schedule. The delivery end date has been revised from June 2025 to June 2026 due to interrupted works caused by contractual and procurement delays.
Q4 24-25 | Department of Education | DE | 3896 | Kindergarten Attendance Program | Education | Analyses and Statistics ,Business Intelligence,Data Management | Delivery of a digital solution to collect kindergarten attendance data to improve child outcomes and to report on performance indicators as required by the Commonwealth Preschool Reform Agreement. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Increased Revenue (Financial) |  | Agile | 2023-02-01 | 2023-07-31 |  | 2023-08-01 | 0 |  | 2023-08-01 |  | 2026-06-30 |  | 20965000 |  | Green | Green | Green | Green | Green | Kindergarten Providers were onboarded during the period. Detailed design for the next phase of the solution commenced with the delivery partner in preparation for deployment in FY26.
Q4 24-25 | Department of Education | DE | 3897 | Oracle Cloud Program Phase 2 | Education | Assets/Materials Management,Financial Management,Reporting | The project will deliver an integrated Oracle Cloud enterprise resource planning and analytics solution to uplift and modernise finance and procurement systems to deliver consistent financial services support across the Victorian Government. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | Agile | 2023-11-06 | 2023-11-10 |  | 2023-11-12 | 0 |  | 2023-11-13 |  | 2025-05-21 |  | 14120000 |  | Green | Green | Green | Green | Green | The Core functionality of the enterprise resource planning and analytics solution has been delivered. The project is now closed.
Q4 24-25 | Department of Health | DH | 3899 | Health Technology Services Application Cloud Migration | Health | Data Management,Development and Integration | Migrate three Health Technology Services applications to the department’s ICT Cloud environments, namely Finance and Material Information System, Client Management System and HealthCollect, to improve data availability, security and reliability. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-05-01 | 2024-05-31 |  | 2024-05-31 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2026-01-31 | 2715200 | 2615000 | Green | Amber | Amber | Red | Amber | Project is Amber pending procurement of services which is impacting schedule.
Q4 24-25 | Department of Education | DE | 3900 | Project and Portfolio Management Platform (PPMP) | Education | Data Management,Document Management ,Management of Process ,Reporting ,Investment Management | PPMP will provide a Microsoft Power Platform-based solution that promotes the visibility and control of real-time and accurate project, program and portfolio information by consolidating all data sources into a single source of truth. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-06-28 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-04 | 2024-08-29 | 2023-08-31 | 2023-09-04 | 415049 |  | 2024-10-21 |  | 2025-06-28 |  | 924410 | 927757 |  |  | Green | Green | Green | The project successfully delivered the Project and Portfolio Management Platform with the business go-live in May 2025 and is now closed.
Q4 24-25 | Department of Government Services | DGS | 3902 | Basic Cyber Security Controls Project | Government and Economy | Security Management | This project will deliver five cyber security controls to improve security control adoption across government, minimising common cyber incidents and meeting national cyber security model. | Closed - Completed | Compliance (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | PRINCE2 | 2023-10-05 | 2024-05-10 |  | 2024-05-11 | 0 |  | 2024-10-01 |  | 2025-06-30 |  | 10000000 |  |  | Green | Green | Green | Green | The project is successfully completed on time within approved budget.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3904 | Inventory Management System Project | Environment and Water | Business Intelligence | The project will deliver a modern, scalable, fit-for-purpose warehouse management system that will allow stock and inventory to be managed and tracked across all state and regional warehouses. | Closed - Completed | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-01-01 | 2023-06-30 |  | 2023-12-21 | 101560 |  | 2023-12-21 |  | 2026-11-20 | 2025-06-30 | 3259441 | 2111017 |  | Green | Green | Green | Green | The project has been successfully completed. It was delivered within the agreed scope budget and ahead of schedule.
Q4 24-25 | Westernport Region Water Corporation | WPR Water | 3906 | Asset Management Information System Replacement | Environment and Water | Assets/Materials Management | The project will replace legacy asset management and work order management systems improving functionality and flexibility to enable more accurate, accessible and comprehensive information for decision-making. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-09-03 | 2025-06-30 | 2025-04-14 | 2025-04-14 | 200000 | 254000 | 2025-04-14 |  | 2026-10-30 |  | 1440000 | [5 empty] | Green | Contract signed with Asset Vision in June 2025. Discovery workshops will commence in August 2025.
Q4 24-25 | Peninsula Health | PEN Health | 3907 | Peninsula Health Project Phoenix (MePACS Refresh) | Health | Customer Relationship Management | A technology refresh of the core MePACS systems with a modern Customer Relationship Management System (CRM) to secure the ongoing viability of the MePACS business. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-06-03 | 2024-10-31 |  | 2024-10-31 | 340000 |  | 2024-11-04 |  | 2025-10-31 |  | 2620000 |  |  |  | Green | Green | Green | Project running through the critical phases of User Acceptance Testing (UAT) then moving to training and delivery phase. On Track.
Q4 24-25 | South East Water | SE Water | 3909 | PULSE CX Optimisation Phase 2 | Environment and Water | Customer Relationship Management | This project will deliver significant uplift to SEW's Customer Relationship Management (CRM) and telephony system. This includes uplift to contact centre efficiency, bolstering data security and introducing more self-service options for customers. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Risk Reduction (Non Financial) | 2025-06-30 | Agile | 2024-09-01 | 2024-09-06 |  | 2024-09-06 | 0 |  | 2024-09-09 |  | 2025-04-30 |  | 2649304 |  |  | Red | Amber | Amber | Green | Project successfully delivered in April.
Q4 24-25 | Monash Health | Monash H | 3911 | Delphi - Oracle Cloud Fusion | Health | Financial Management | The project will implement Oracle software as a service to uplift management of finance, procurement, enterprise performance, project management, supply chain, and warehouse, enabling more efficient and effective business processes for Monash Health. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-08-07 | 2024-09-13 |  | 2024-09-13 | 50000 |  | 2024-09-16 |  | 2025-12-26 | 2025-12-31 | 17631000 |  |  | Green | Green | Green | Green | Build activities for the Enterprise Resource Planning (ERP) and Supply Chain Management (SCM) modules are proceeding according to plan. Preparations for testing and cutover activities are actively underway.
Q4 24-25 | Monash Health | Monash H | 3912 | Maternity Digital Transformation Project | Health | Management of Process | The project will implement EMR and breast milk management module onto a single EMR platform, supporting a single view of the patient's medical record, improving clinical outcomes for both mother and baby. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-07-01 | 2024-10-31 | 2024-04-04 | 2024-04-04 | 0 | 0 | 2024-11-01 |  | 2026-05-27 |  | 11522379 |  |  |  |  | Amber | Green | The project is progressing as planned, with scope confirmed and budget clarified. The kick-off is complete, and current activities are on schedule.
Q4 24-25 | Kardinia Park Stadium Trust | KPST | 3914 | Southern Scoreboard Replacement Project | Culture, Sport and Recreation | Communication,Content Management | Replacement of the life expired Southern Scoreboard at GMHBA Stadium to support event delivery, emergency management and customer fan experience. | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) | 2025-05-31 | Vendor provided methodology | 2024-05-05 | 2024-05-05 |  | 2024-05-05 | 0 |  | 2024-05-06 |  | 2025-03-28 |  | 3000000 |  |  | Green | Green | Green | Green | Project completed. Financial reconciliation underway.
Q4 24-25 | Barwon Region Water Corporation | BR Water | 3915 | C1062 - Works and Asset Management | Environment and Water | Assets/Materials Management | Improve strategic and operational asset management and service delivery through the implementation of Maximo Works Management providing benefits such as, a more financially sustainable business and keeping bills affordable for all. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2025-03-31 | 2025-07-01 |  | 824310 | 2164000 | [11 empty] | The BWG board approved the business case and endorsed the preferred System Implementer in June. The project will commence Delivery phase in July with the first phase to upgrade Maximo from version 7.6 to 9.0. As part of the last qtr., project enablement activities were bought forward to increase project success.
Q4 24-25 | Barwon Region Water Corporation | BR Water | 3916 | C1061 - Customer Experience (CX) Foundations | Environment and Water | Customer Relationship Management | Ensure modern high quality and sustainable customer and employee experience through a CRM & Customer Portal. Benefits are maintaining high quality customer service and enhanced financial performance & operational efficiency. | Closed - Completed | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-12-01 | 2025-03-31 | 2024-06-30 | 2024-06-30 | 1292283 | 960819 | 2024-07-01 |  | 2025-06-30 |  | 960819 | [5 empty] | Green | The foundation document set is now available and these artefacts will provide input into a future enterprise customer relationship management platform implementation. The project is now complete.
Q4 24-25 | Department of Families, Fairness and Housing | DFFH | 3917 | Public Housing Maintenance Modernisation Technology Enablement Program | Community Services | Development and Integration | Uplift digital capability of Homes Victoria systems including new housing maintenance portal, improvements to HiiP system, and integration capability with Contractor Work Systems, providing greater process efficiencies and ease of use by tenants. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-01 | 2024-10-11 |  | 2024-10-11 | 1214790 |  | 2024-10-11 |  | 2026-06-30 |  | 23066733 | 25623840 |  |  | Green | Red | Red | Program status is red due to continuing delays primarily caused by constraints in accessing required services. Impact to schedule is being assessed but not expected to impact on the overarching Public Housing Maintenance Modernisation schedule. Project progressing to revised cost.
Q4 24-25 | Victorian Gambling and Casino Control Commission | VGCCC | 3918 | Compass – Liquor and Gambling Information System (LaGIS) replacement project | Law and Justice | Customer Relationship Management | A new regulatory system to replace the legacy compliance management system. The project will remediate and uplift VGCCC's ICT infrastructure, improving ICT capabilities and enabling effective, risk-based, and intelligence-led regulatory approach | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial) | 2025-06-06 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-04 | 2024-08-30 |  | 2024-08-30 | 36000 |  | 2024-09-02 |  | 2025-06-06 |  | 1650000 |  |  | Green | Green | Green | Green | The project scope has been delivered within budget and on schedule. The legacy LaGIS system is no longer in use, and the transition to the new system was successful.
Q4 24-25 | South East Water | SE Water | 3920 | Meeting Room Technology Upgrade | Environment and Water | Assets/Materials Management | Upgrades to the technology across selected meeting rooms, training rooms and board room at SEW's head office in Frankston. Existing technology was installed in 2015 and is being updated to better meet the needs of the hybrid workplace. | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-04-30 | Waterfall | 2024-01-01 | 2024-02-09 |  | 2024-02-09 | 0 |  | 2024-02-12 |  | 2024-12-31 | 2025-04-30 | 1024450 | 1030000 |  | Green | Green | Green | Green | Remaining scope of project has been delivered and outstanding issues resolved, and solution handed over to operations team for ongoing management. Project closed in Q4.
Q4 24-25 | Department of Families, Fairness and Housing | DFFH | 3921 | Automated System Integration of the Victorian Housing Register (online) Application | Community Services | Records Management | Moving the Victorian Housing Register Application to an automated integrated solution, thereby improving the timeliness and capacity to manage an increase in volumes at an office level, improving client experience with faster feedback. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-28 | 2024-06-28 |  | 2024-06-28 | 192450 |  | 2024-07-15 |  | 2025-06-30 | 2025-10-31 | 1614264 | 2506256 |  | Amber | Red | Green | Red | Project is progressing but is Red due to constraints in accessing required services. Impact to schedule to be revised and submitted to steering committee for approval in next reporting period.
Q4 24-25 | Department of Government Services | DGS | 3922 | Cyber Assurance and Maturity Uplift | Government and Economy | Security Management | The project will provide cyber assurance and uplift support to strength cyber defences across government and meeting national cyber security model. | Closed - Completed | Compliance (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | PRINCE2 | 2023-10-05 | 2024-05-10 |  | 2024-05-11 | 0 |  | 2024-10-01 |  | 2025-06-30 |  | 4000000 |  |  | Green | Green | Green | Green | The project is successfully completed on time within approved budget.
Q4 24-25 | South East Water | SE Water | 3923 | Acumen Phase 2 | Environment and Water | Business Intelligence,Data Management | Phase 2 of Acumen will deliver foundation components, including architecture review and data preparation for ingestion and modelling. This will deliver key foundational elements necessary to support future phases. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-01-01 | 2024-02-29 |  | 2024-02-29 | 0 |  | 2024-02-29 |  | 2025-04-30 | 2025-09-30 | 3600000 | 6585000 |  | Green | Amber | Green | Amber | The project is reporting AMBER due to delays to key milestones relating to development and ingestion of new system data sources into the Acumen program.
Q4 24-25 | South East Water | SE Water | 3924 | Information Management Strategy Delivery | Environment and Water | Business Intelligence,Data Management,Reporting | Program of work delivering multiple initiatives that is delivering on the Information Strategy including - Enterprise Content Management Data & Information Management Analytics & Reporting. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2023-06-01 | 2023-06-30 |  | 2023-09-26 | 0 |  | 2023-09-26 |  | 2025-07-31 |  | 1859425 |  |  | Red | Red | Red | Amber | The project has recommenced after key roles on the project have been recruited. Project remains AMBER until a plan to return to green is established.
Q4 24-25 | South East Water | SE Water | 3925 | Lentic Performance Enhancements | Environment and Water | Communication | Optimization of IoT platform to ensure scalability and optimal performance within the boundaries of the current architecture. This will ensure the IoT platform will support the mass roll out of digital meters across SEW network. | Delivery | Risk Reduction (Non Financial) |  | Waterfall | 2024-03-01 | 2024-04-18 |  | 2024-06-05 | 0 |  | 2024-08-01 |  | 2025-12-31 |  | 1161000 |  |  | Green | Green | Amber | Amber | Schedule reporting as AMBER mainly driven by delays with upcoming deliverables. Project investigating options to combine upcoming releases to keep the project on track.
Q4 24-25 | Transport Accident Commission | TAC | 3927 | Continuous Delivery 25 | Transport and Vehicles | Systems Management | The Continuous Delivery project provides a robust, scalable and mature mechanism to deliver high business value changes to TAC Claims systems every month. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | Agile | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-01 |  | 2025-06-30 |  | 3110724 |  |  | Green | Green | Green | Green | Project complete on time and on budget. Three Avanti releases deployed on schedule.
Q4 24-25 | Gippsland Health Alliance | GHA | 3928 | Payroll and Talent Modernisation (HRIS) | Health | Human Capital / Workforce Management | The project involves implementing a single instance of SAP SuccessFactors across eleven agencies in Gippsland. This initiative aims to modernise processes and systems, enhancing efficiency and collaboration among the agencies. | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2022-02-18 | 2022-05-20 |  | 2023-02-17 | 180000 |  | 2023-04-10 |  | 2025-06-27 |  | 1600000 |  |  | Amber | Amber | Amber | Amber | The PTM SuccessFactors Project is live at one regional site. Planning for rollout to additional sites is underway. The project is currently rated Amber due to resourcing constraints, with a revised delivery timeline pending governance approval.
Q4 24-25 | South East Water | SE Water | 3930 | Cyber & Data Security Uplift | Environment and Water | Security Management | Uplift in SEW's Cyber & Data Security through the implementation and enhancement of key security and governance controls. The project will enhance platform performance to improve data security and minimise risks for the organisation. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Risk Reduction (Non Financial) | 2025-05-16 | Agile | 2023-12-01 | 2024-06-30 |  | 2024-06-30 | 68900 |  | 2024-07-01 |  | 2025-04-30 |  | 1881100 | 2015500 |  | Amber | Green | Green | Green | Project successfully delivered and closed out in Q4.
Q4 24-25 | Transport Accident Commission | TAC | 3931 | Strategic Analytics Program Phase 2 | Transport and Vehicles | Business Intelligence | Build capability for both analysts & the broader enterprise in working optimally to deliver use cases from a prioritised backlog that will result in well managed & trusted data, improved customer & workforce satisfaction, platform efficiencies. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-01 |  | 2026-06-30 |  | 11000000 |  |  | Green | Green | Green | Green | Strong finish to the year, all milestones met and planning for FY25/26 complete.
Q4 24-25 | Melbourne Water | MELB Water | 3932 | Cyber Defence Initiatives | Environment and Water | Security Management | Redesign the existing SOC capability in line with the new Security Operations Operating Model. Deliver a better asset discovery and inventory capability, providing cyber control coverage assurance to the organisation. | Initiated |  |  | PMBoK | 2024-07-26 | 2025-02-20 | 2025-07-31 |  | 0 | [12 empty] | As at 20250630: Business Case expected to be approved in July
Q4 24-25 | WorkSafe Victoria | WorkSafe | 3933 | Strategic Integration Platform | Employment, Skills and Workplace | Systems Management | Integration technology connects systems and data across platforms. This project will move existing integrations to the Strategic Integration Platform a modern cloud-based solution that reduces failures and speeds recovery benefitting all users. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2025-10-30 | 4597071 | 7089351 |  | Green | Green | Amber | Red | Due to some further technical challenges and mandatory security infrastructure changes the project will raise a change request to extend the timeline and increase the budget.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 3934 | Licensing CRM (Customer Relationship Management) FY25 | Employment, Skills and Workplace | Customer Relationship Management | Transition of the remaining 5 license journeys from the legacy mainframe. This completes the transition of License Management capability to the CRM, unifying business processes, centralising data, and enhancing both customer and employee experiences. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 | 2026-03-31 | 4466242 | 6958211 |  | Green | Green | Red | Green | On track
Q4 24-25 | WorkSafe Victoria | WorkSafe | 3935 | Continuous Improvement CRM (Customer Relationship Management) | Employment, Skills and Workplace | Customer Relationship Management | CRM Continuous Improvement delivers ongoing enhancements to the CRM. These system enhancements deliver increased efficiencies, streamline processes, and improve the user experience for both WorkSafe employees (Advisors, Inspectors) and clients. | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-06-30 | Agile | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 0 |  | 2024-07-01 |  | 2025-06-30 |  | 4840718 | 4920415 |  | Green | Green | Green | Green | Project closed
Q4 24-25 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3938 | SEC Corporate ERP System | Energy and Resources | Financial Management,Human Resources,Supply Chain Management | The SEC Corporate ERP system implementation project will select and implement an integrated Finance, HR and Procurement system to meet the requirements of SEC. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-12 | 2024-11-30 | 2024-10-30 | 2024-10-30 | 390000 | 210000 | 2024-11-01 |  | 2025-06-30 | 2025-07-25 | 1390000 |  |  |  | Green | Green | Green | Key functionality has been delivered into production and is currently in use by the business. Project is under hyper care with the vendor and in final phases of project closure.
Q4 24-25 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 3940 | SEC Energy Markets Projects | Energy and Resources | Financial Management | This ETRM Solution will provide an integrated suite of systems and processes to meet the SEC’s requirements of Deal capture, Settlements validation, Authorised trader/mandate register and Risk management. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-17 | 2024-10-14 |  | 2024-10-18 | 195172 |  | 2024-10-18 |  | 2025-07-16 |  | 3376919 |  |  |  | Green | Green | Green | Project is tracking to all key metrics and key functionality delivered to the business. Currently in hypercare with the vendor.
Q4 24-25 | Independent Broad-based Anti-corruption Commission | IBAC | 3941 | Case Management System Enhancement Project | Government and Economy | Business Intelligence,Collaboration | This project is to deliver enhancements to IBAC's case management system and improvements to data maturity in the form of analytics, reporting and dashboard outputs. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-03 | 2024-12-31 | 2025-01-31 | 2025-01-31 | 0 | 270000 | 2025-02-01 |  | 2026-06-30 |  | 2443584 | 2443584 |  |  |  | Amber | Amber | The project remains at Amber due to the additional time required to remediate issues identified during the first iteration of User Acceptance Testing. It is noted that in Q3, the project also reported as Amber due to delays in the commencement of User Acceptance Testing. This represents a schedule-related risk only, with no impact to the approved budget, overall project timeline, and scope.
Q4 24-25 | Yarra Valley Water | YV Water | 3943 | Digital Meter Integrated Software Solution (HES/MDMS) | Environment and Water | Analyses and Statistics ,Assets/Materials Management,Knowledge Discovery ,Tracking and Workflow,Visualisation | Implementation of an integrated software solution for an Internet of Things Head End System (IoT HES) and Meter Data Management System (MDMS) to enable YVW’s digital water metering and IoT strategy which plans to deploy around one million digital met | Delivery | Efficiency/Productivity (Non Financial) |  | Agile | 2022-08-01 | 2023-12-31 |  | 2024-01-09 | 1062000 |  | 2024-01-10 |  | 2025-06-30 | 2025-12-31 | 6678000 |  |  | Green | Green | Green | Green | The project is tracking well against scope and budget, with a minor schedule delay to one milestone. The software platform is live with over 22k meters deployed with enhanced features to identify customer leaks. Large meters from EDMI with new protocol has been tested in Production.
Q4 24-25 | Yarra Valley Water | YV Water | 3945 | WorksPortal System and Asset Creation Replacement | Environment and Water | Customer Relationship Management | The current WorksPortal System is reaching end of life with support expiring by July 2026. As the system relates to asset creation and revenue, a replacement is required. | Delivery | Compliance (Non Financial), Customer Satisfaction (Non Financial), Reputation (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-07-01 | 2025-03-31 | 2025-05-31 | 2025-06-19 | 650000 | 736000 | 2025-06-19 |  | 2026-04-30 |  | 3936260 | [5 empty] | Green | Project has moved into Delivery
Q4 24-25 | Yarra Valley Water | YV Water | 3946 | Land Development System (easyACCESS) Replacement | Environment and Water | Customer Relationship Management | Full replacement of the current easyACCESS Land Development portal with a Salesforce solution, before the portal reaches end of life | Initiated |  |  | Agile | 2024-07-01 | 2025-06-30 | 2025-12-31 |  | 1772100 | 3795600 | [11 empty] | The Request for Tender (RFT) was published April 2025 and the RFT closed on 27 June 2025. Responses received are currently being evaluated.
Q4 24-25 | Yarra Valley Water | YV Water | 3947 | MAXIMO 2025 UPGRADE | Environment and Water | Data Management | To upgrade Maximo software version 7.6 to version 9 to ensure continued support, enhance operational efficiency and leverage additional functionalities | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-01-01 | 2025-01-15 | 2025-01-08 | 2025-01-08 | 697090 |  | 2025-01-08 |  | 2025-12-31 |  | 1723910 |  |  |  |  | Green | Amber | The project remains on track for completion by the planned end date. Development has been completed and System Testing is now underway. Due to the project’s complexity, additional resources have been engaged, resulting in a forecasted minor cost overrun for which a change request is being prepared
Q4 24-25 | Melbourne Water | MELB Water | 3948 | End User Computing Lifecycle Renewal FY24-26 | Environment and Water | Assets/Materials Management | Staff have been provided devices including laptops, tablets, heat sets and mobile phones to perform their tasks. These devices need to be regularly updated to ensure suitable performance and enabling the use of modern applications. | Initiated |  |  | PRINCE2 | 2024-09-30 | 2025-02-06 | 2025-08-08 |  | 0 | [12 empty] | As at 20250630: Business Case to be submitted Q1 FY25/26.
Q4 24-25 | Melbourne Water | MELB Water | 3949 | Identity and Access Management Initiatives | Environment and Water | Security Management | Process uplift, technology build and onboarding to the current identity access platform. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-05-21 | 2024-12-11 | 2024-12-11 | 0 |  | 2024-12-11 |  | 2026-06-30 |  | 4807000 | 5483137 |  |  | Green | Green | Red | As at 20250630: Project Change request to be submitted in Q1 FY25/26, will revert to green. This is for reallocation funding between cost centres. No additional spend by organisation.
Q4 24-25 | Melbourne Water | MELB Water | 3950 | Intranet Renewal | Environment and Water | Communication | Renew or replace current Melbourne Water Intranet, including full investigation of options and user impacts. Re-imagine employee access to internal information. | Initiated |  |  | PMBoK | 2024-08-26 | 2024-12-18 | 2025-09-30 |  | 0 | [12 empty] | As at 20250630: RFP in progress to inform Business Case submission.
Q4 24-25 | Melbourne Water | MELB Water | 3951 | IT Facilities End of Life Hardware Replacement | Environment and Water | Assets/Materials Management | Replacement of critical IT facilities hardware (Air conditioners Uninterrupted Power Supply batteries) that are coming out of warranty or service contracts and due to 24/7 use require replacement. | Delivery | Cost Reduction (Financial), Risk Reduction (Non Financial) |  | PMBoK | 2023-12-05 | 2024-09-09 |  | 2024-09-09 | 0 |  | 2024-09-09 |  | 2025-03-31 | 2025-07-31 | 1076437 |  |  | Green | Green | Green | Green | As at 20250630: Implementation is complete and project is progressing to closure activities in Q1 FY25/26
Q4 24-25 | Melbourne Water | MELB Water | 3952 | Privilege Access Management Initiatives | Environment and Water | Systems Management | This project aims to implement a comprehensive Privileged Access Management (PAM) system to enhance security by onboarding critical accounts across network and operational technology environments. The investment supports robust identity governance. | Delivery | Risk Reduction (Non Financial) |  | PMBoK | 2024-07-26 | 2025-03-21 | 2024-12-12 | 2024-12-12 | 0 |  | 2024-12-12 |  | 2026-06-30 |  | 2290000 | 3060378 |  |  | Green | Green | Red | As at 20250630: Project Change request to be submitted in Q1 FY25/26, will revert to green. This is for reallocation funding between cost centres. No additional spend by organisation.
Q4 24-25 | Department of Transport and Planning | DTP | 3953 | OneDigital Workplace | Transport and Vehicles | Customer Preferences,Development and Integration ,Organisational Management ,Security Management ,Systems Management | Delivering a new Standard Operating Environment and operating model for the DTP so that all users can access a modern and consistent desktop environment. Includes rationalisation of ITSM tools (ServiceNow). | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2026-06-30 | 2025-02-28 | 2025-02-28 | 10000000 | 0 | 2025-03-03 |  | 2026-06-30 |  | 10000000 |  |  |  |  | Green | Green | Overall program status is green and is on track.
Q4 24-25 | Melbourne Water | MELB Water | 3954 | Standalone Server Refresh | Environment and Water | Assets/Materials Management | Standalone servers at or approaching end of life &/or end of support require upgrading to meet ongoing operational requirements. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-08-09 | 2024-10-30 |  | 2024-11-13 | 0 |  | 2024-11-13 |  | 2026-03-12 |  | 1992000 |  |  |  | Green | Green | Green | As at 20250630: Tracking to plan.
Q4 24-25 | Melbourne & Olympic Parks | M&OP | 3955 | End of Life Switch Replacement 2024/25 | Culture, Sport and Recreation | Systems Management | The project will replace end-of-life hardware to maintain support for the network switch environment, enabling the organisation to minimise legacy system risks and improve security. | Delivery | Risk Reduction (Non Financial) |  | Agile | 2024-05-01 | 2024-07-01 |  | 2024-07-01 | 0 |  | 2024-07-15 |  | 2025-06-30 | 2025-10-31 | 2750000 |  |  | Green | Green | Amber | Amber | Hardware staging activities completed along with initial device configuration Project reporting Amber due to extended delivery phase caused by a delay in scoping documentation. Scoping documentation expected in Q1 and project will be back on track.
Q4 24-25 | Department of Education | DE | 3956 | Automated Briefing and Correspondence (ABC) Implementation | Education | Content Management,Data Management,Document Management ,Management of Process ,Reporting ,Tracking and Workflow | The project will deliver a workflow solution for managing all departmental briefings and correspondence. This solution will enhance the depts digital capabilities by utilising existing Cloud Service. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-12 | 2023-07-04 |  | 2023-09-05 | 0 |  | 2024-07-29 |  | 2025-03-07 | 2025-12-31 | 2657628 |  |  | Green | Green | Amber | Green | The project was re-baselined in June 2025 due a change in approach at the whole of Victorian government level and the analysis of additional requirements, extending the project to Q2FY26. Work on the revised scope commenced during the period.
Q4 24-25 | Environment Protection Authority | EPA | 3959 | MAJ140 - Finance System Upgrade | Environment and Water | Financial Management | Migrating from current TechnologyOne FinanceOne Ci solution to TechnologyOne FinanceOne CiA solution to provide extended vendor support and to provide EPA with enhanced Finance and Procurement functionality. The project will alleviate many pain point | Delivery | Cost Reduction (Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2024-10-22 |  | 2024-10-23 | 0 |  | 2024-10-24 |  | 2025-06-30 | 2025-08-30 | 1635000 |  |  |  | Amber | Amber | Amber | The project change request has been approved to extend the timeline to the end of August, along with an additional $100,000 in funding to support the revised Go-Live.
Q4 24-25 | Department of Education | DE | 3961 | Securing Connected Learners (SCL) Program – Phase 2 | Education | Development and Integration ,Security Management ,Systems Management | SCL is a ‘high profile’ program of work creating enhanced security capabilities for schools initially addressing child safety & security risks in schools by transitioning schools to platforms with enhanced cyber security features. | Delivery | Cost Avoidance (Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-06-01 | 2024-06-03 |  | 2024-06-03 | 0 |  | 2024-06-03 |  | 2025-06-30 | 2025-12-31 | 3100000 | 6098000 |  | Amber | Amber | Amber | Amber | The project is reporting amber due to complexity related risks and school server readiness. The project is managing the risks and working to mitigate any financial and schedule impact.
Q4 24-25 | Department of Education | DE | 3962 | Senior Secondary Pathways Reform Transformation | Education | Customer Relationship Management,Data Management,Forms Management,Tracking and Workflow | The Program will digitise streamline and enhance the management of work-based learning delivering an exceptional learning and development experience for every Victorian Secondary School ensuring pathways are optimised for students. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Social Improvement (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-04-01 | 2024-04-01 |  | 2024-04-01 | 0 |  | 2024-04-01 |  | 2025-06-30 |  | 14190000 | 14958674 |  | Amber | Amber | Amber | Green | This phase of the program is now closed following the successful delivery of the two applications. A new project is being established to deliver further applications in FY26.
Q4 24-25 | Department of Education | DE | 3963 | 50 Early Learning Childcare Centres - Technology Components | Education | Customer Relationship Management | The project will deliver the required technology components in 50 ELC centres to support the Victorian Government initiative in broader early learning, enabling great start for young Victorians. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Reputation (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-15 | 2024-03-15 |  | 2024-03-18 | 0 |  | 2024-03-18 |  | 2032-06-30 |  | 2108035 | 4205068 |  | Green | Green | Green | Green | The project is on track. The second phase launch is planned for Q1 Calendar Year 2026. Planning for the 2026 technology infrastructure delivery roadmap is underway with the 2025 IT roadmap in place.
Q4 24-25 | State Revenue Office | SRO | 3964 | Short Stay Levy | Government and Economy | Development and Integration | A levy on short stay accommodation in Victoria was implemented on 1 January 2025. The short stay levy aims to increase the supply of properties available for long-term accommodation. This project sets up the systems to administer the levy. | Delivery | Social Improvement (Non Financial) |  | Agile | 2024-05-23 | 2024-06-30 |  | 2024-06-30 | 81000 | 60000 | 2024-07-01 |  | 2025-06-30 | 2025-08-30 | 3080000 |  |  | Green | Amber | Green | Green | Phase 1-4 have been delivered as of 30 June 2025 with warranty period through to 30 August 2025.
Q4 24-25 | State Revenue Office | SRO | 3965 | Vacant Residential Land Tax 2 | Government and Economy | Development and Integration | This project will expand the Vacant Residential Land Tax (VRLT) system to collect and administrate VRLT across all Victoria properties from January 2025 and underdeveloped residential land in Greater Melbourne areas from January 2026. | Delivery | Social Improvement (Non Financial) |  | Agile | 2024-05-23 | 2024-06-30 |  | 2024-06-30 | 35000 |  | 2024-07-01 |  | 2026-06-30 |  | 1927652 | 4738171 |  | Amber | Amber | Amber | Green | The project returned to green in Q4 2024/25 with the 2026 scope confirmed and resources onboarded. The budget increase is to reflect the full scope delivery including the 2026 changes.
Q4 24-25 | Department of Transport and Planning | DTP | 3967 | VIDA - Victorian Health Building Authority (VHBA) Integr8 | Transport and Vehicles | Collaboration ,Financial Management,Human Capital / Workforce Management ,Human Resources,Investment Management,Organisational Management | The VHBA Integr8 Program has been established to support VHBA to enact their Machinery of Government changes, with a specific focus on transitioning to the VIDA Information and Technology systems and supporting a smooth transition for VHBA employees. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-09 | 2024-11-11 |  | 2024-11-12 | 250000 |  | 2024-11-12 |  | 2025-11-30 |  | 8258958 |  |  |  | Green | Green | Green | Successfully migrated Identity and Corporate Systems (HR Finance Procurement and Project Controls) to the target state. Next workstream to go-live is M365 and this will conclude all Business Value Group (BVG) 1 deliverables.
Q4 24-25 | Alfred Health | ALFRED | 3968 | Disaster Recovery | Health | Security Management | The Disaster Recovery project will enhance ICT infrastructure for disaster recovery, prioritizing patient safety and data integrity by establishing a robust, adaptable ICT environment that maintains continuous operations during disruptions. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-10-21 |  | 2024-10-21 | 148217 | 69382 | 2024-10-28 |  | 2026-07-01 |  | 1171783 | 1250618 |  |  | Green | Green | Green | The Project is on track.
Q4 24-25 | Greater Western Water Corporation | GW Water | 3971 | Systems Readiness | Environment and Water | Communication,Content Management,Customer Initiated Assistance,Customer Relationship Management,Data Management,Development and Integration ,Document Management ,Financial Management,Forms Management,Management of Process ,Records Management ,Reporting ,Systems Management,Tracking and Workflow | This project was established to focus on uplifting the customer ecosystem with a focus on core billing being operationally sound and to support customer facing processes including stabilising IT infrastructure and new service demands | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-07-04 |  | 2024-07-04 | 1593505 |  | 2024-07-04 |  | 2025-06-30 | 2025-09-30 | 4406495 | 5335740 |  | Amber | Amber | Amber | Amber | Remaining deliverables and remediation of defects continues into the next quarter Program is amber due to reprioritisation of scope.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3977 | Energy Customer Relationship Management (CRM) Project | Government and Economy | Customer Relationship Management | The Energy CRM Project will deliver a customer management system to enable DEECA's Energy Group to deliver best practice stakeholder engagement and more efficient government processes. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-04 | 2024-12-11 |  | 2024-12-11 | 150000 |  | 2024-12-12 |  | 2025-06-30 | 2025-08-15 | 1277120 |  |  |  | Green | Amber | Green | The project is tracking well against scope budget and schedule. The project has returned to green. Schedule has been re-baselined to include additional scope.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3980 | FireWeb Decommissioning Project | Emergencies and Safety | Management of Process | The FireWeb Decommissioning Project will replace the legacy system FireWeb infrastructure to improve the accessibility of the information. This infrastructure will be DEECA's primary source for Fire Management. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2028-06-30 |  | 5047000 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3981 | Emergency Management (EM) Deployment Project | Emergencies and Safety | Management of Process | The EM Deployment project will deliver a modern system to plan and coordinate the commitments and resources for bushfire and other emergency incidents to increase DEECA's capabilities to manage these incidents effectively and in a timely manner. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-06-30 |  | 2024-06-30 | 0 |  | 2024-07-01 |  | 2026-12-31 | 2026-12-31 | 1223000 |  |  |  | Green | Green | Green | The project is tracking well against scope, budget and schedule.
Q4 24-25 | Department of Government Services | DGS | 3982 | Service Victoria - Firearms & Private Security Digital Program - Phase 1 | Government and Economy | Customer Initiated Assistance,Management of Process | The project will deliver a minimum viable product to digitise the Firearms licence renewal process, in addition to enabling Firearms licence holders to obtain and securely store their licences in a digital form through Service Victoria app | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-09-01 | 2024-03-01 |  | 2024-03-01 | 0 |  | 2024-03-01 |  | 2025-06-30 | 2025-08-05 | 2239255 | 1800000 |  |  | Green | Green | Green | The project is on track against approved scope budget and schedule with delivery of the Pilot planned for early August 2025
Q4 24-25 | Greater Western Water Corporation | GW Water | 3983 | Property Information | Environment and Water | Communication,Customer Relationship Management,Data Management,Management of Process ,Systems Management,Analyses and Statistics ,Assets/Materials Management,Content Management,Development and Integration ,Document Management ,Financial Management,Forms Management,Records Management ,Reporting ,Routing and Scheduling,Search ,Tracking and Workflow | This project will focus on remediating critical data and technology components within GWWs customer property and billing systems to meet KPIs, expected service levels, and customer satisfaction objectives | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-25 | 2024-07-25 |  | 2024-07-25 | 1 |  | 2024-07-25 |  | 2025-03-31 | 2025-09-30 | 13708801 | 13999999 |  |  | Amber | Amber | Amber | Remaining deliverables and remediation of defects continues into the next quarter Program is amber due to reprioritisation of scope.
Q4 24-25 | Department of Health | DH | 3984 | Enterprise Payments Platform | Community Services | Financial Management | Deliver a payments platform to replace existing manual processes and improve system workflows to ensure timely payments to citizens for programs in scope (Non Mains Energy Concessions, Care Allowance). | Closed - Completed | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | Agile | 2024-06-28 | 2024-07-02 |  | 2024-07-02 | 0 |  | 2024-07-02 |  | 2025-06-30 |  | 1670938 | 1667999 |  |  | Amber | Red | Green | Project has successfully delivered and closeout activities are underway.
Q4 24-25 | Peninsula Health | PEN Health | 3985 | Peninsula Health Replacement of legacy Citrix virtual desktop environment & virtual server infrastructure | Health | Systems Management | Replacement of legacy Virtual Desktop and Converged Infrastructure at Frankston Hospital providing clinical application access to all sites, increasing usability and access for all staff to applications and data, including Video conference/telehealth | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2024-03-04 | 2024-10-18 |  | 2024-10-18 | 10000 |  | 2024-10-18 | 2024-10-21 | 2026-02-27 |  | 7329269 | 7832065 |  |  | Green | Green | Green | Project is tracking to schedule.
Q4 24-25 | Department of Health | DH | 3986 | Victorian Perinatal Data Collection (VPDC) Transition to In House Cloud Solution | Health | Data Management | Deliver a cloud based solution to manage the ingestion, validation and reporting of obstetric conditions, procedures and outcomes relating to every birth in Victoria, to contribute to improvements in the health of mothers and babies. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-12-03 |  | 2024-12-03 | 94524 |  | 2024-12-03 |  | 2025-06-30 |  | 965476 | 965876 |  |  | Green | Amber | Green | Project successfully delivered and closeout activities underway.
Q4 24-25 | Department of Health | DH | 3987 | Donor Conception Register IT System | Health | Customer Relationship Management | Deliver a new IT system to manage Victoria's donor conception registers and allow applicants (donors, donor-conceived persons', parents, and their families) to request information under the legislation. | Postponed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial) | 2024-09-01 | Agile | 2024-01-15 | 2024-03-26 |  | 2024-03-26 | 7800 |  | 2024-04-01 |  | 2025-06-30 |  | 1522446 |  |  |  | Green | Green | Red | The project has delivered major components of the system functionality. Project remains on hold pending completion of substantial work on data remediation and approval of required funding to complete.
Q4 24-25 | Department of Health | DH | 3988 | Oracle 11i Hardware upgrade | Community Services | Financial Management | Replace aged Oracle 11i hardware, and upgrade the operating system, to ensure continued support and reduce hardware failures, maintaining system stability for DFFH and DH's financial management needs. | Closed - Completed | Risk Reduction (Non Financial) | 2025-06-30 | PRINCE2 | 2024-05-01 | 2024-10-08 |  | 2024-10-08 | 664257 |  | 2024-10-08 |  | 2025-06-30 |  | 1395743 |  |  |  | Green | Green | Green | Project has successfully delivered and closeout activities are underway.
Q4 24-25 | South East Water | SE Water | 3989 | CRUX - Stabilisation | Environment and Water | Financial Management | Uplift of ERP solution implemented in 2023. Including Finance Procurement & Project Management functions. | Delivery | Cost Reduction (Financial) |  | Waterfall | 2024-07-01 | 2024-12-20 |  | 2024-12-20 | 0 |  | 2025-01-27 |  | 2026-01-30 |  | 3510000 |  |  |  |  | Green | Green | Project tracking well to scope and budget. Multiple releases of enhanced functionality released in Q4 across Procurement, Projects & Finance.
Q4 24-25 | Department of Health | DH | 3990 | IT Asset Management Information System | Health | Assets/Materials Management | Enhance the existing software management system to incoroporate all department software to help ensure software compliance and reduce ongoing licensing costs. | Closed - Completed | Compliance (Non Financial), Cost Reduction (Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-30 | 2024-05-06 |  | 2024-05-06 | 391252 |  | 2024-05-06 |  | 2025-06-30 |  | 1066028 | 752652 |  |  | Green | Green | Green | Project has successfully delivered and closeout activities are underway.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 3991 | Victorian Water Register (VWR) Evolve Project | Environment and Water | Development and Integration | The VWR Evolve Project will uplift the Victorian Water Register to a supported platform to improve the integrity security and reliability of Victoria's water market and enable future improvements in service delivery and information sharing. | Initiated |  |  | PRINCE2 | 2024-07-01 | 2025-05-31 | 2026-03-31 |  | 0 | 4233990 | [11 empty] | A Proof of Concept was successfully completed to assess the feasibility of uplifting the Victorian Water Register to a new supported platform. During the quarter, the project's Business Case was finalised and approved, and the project received approval to commence a new procurement to secure a suitable Implementation Partner to support project execution. As a result, the Planned 'Project Initiation' End Date has been re-baselined to incorporate this additional procurement period.
Q4 24-25 | Melbourne Water | MELB Water | 3992 | Routine Telecommunications Upgrades FY24-26 | Environment and Water | Assets/Materials Management | Upgrade and replacement of degrading IT network cabling and devices - including microwave dishes 4G boosters WAPs and GWIP services. | Initiated |  |  | PMBoK | 2024-10-04 | 2025-02-13 | 2025-08-01 |  | 0 | [12 empty] | As at 20250630: Business case to be submitted.
Q4 24-25 | Eastern Health | EH | 3993 | Blackburn SurgiNet, Anaesthesia and Device Integration Project | Health | Development and Integration | The Project extends the existing EMR Surginet, Anaesthesia Modules and device integration footprint from Box Hill extending to Blackburn Public Surgical Centre, enhancing patient outcomes through delivering consolidated workflows | Closed - Completed | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) | 2025-05-28 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-12-01 | 2025-01-31 |  | 2025-02-28 |  |  | 2025-02-28 |  | 2025-05-30 |  | 2680000 | 1530303 |  |  |  | Green | Green | Transition to a live state has been taken up well by the Blackburn Public Surgical Centre. The Leadership team have endorsed the successful deployment of new functionality for the operational teams on 28th April 2025 with Hypercare support extending through to 12th of May. A Post Implementation Review has been conducted with the Site Leadership team and all recommendations noted to benefit future planning
Q4 24-25 | Eastern Health | EH | 3994 | Eastern Health EMR and Digitisation in the home | Health | Development and Integration | This project implements the EMR workflows across Care@Home services at Eastern Health alongside new integrated electronic logistics and fleet management applications to improve the coordination and delivery of care outside the hospital walls. | Delivery | Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-06-28 | 2023-06-28 |  | 2023-06-28 | 420139 |  | 2024-12-06 |  | 2025-08-31 |  | 4832935 |  |  |  | Green | Green | Amber | Return to green in place with re-baselined timeline agreed with Steering Committee
Q4 24-25 | Eastern Health | EH | 3996 | Eastern Health EMR Mobility and Enterprise Extension (Acute) | Health | Development and Integration | The EMR Mobility and Extension (Acute) Program aims to expand EMR footprint at Angliss and Maroondah Hospitals, simplify clinician workflows and patient information access, and implement EMR Mobility solutions while decommissioning legacy systems. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2025-02-28 |  | 2025-02-28 | 0 |  | 2025-03-01 |  | 2025-12-15 |  | 9979000 |  |  |  |  | Green | Green | The Project Implementation Phase is well underway with overarching Test Change/Training and Communications Plans completed. Functional designs are nearing completion with build and testing activities occurring in parallel where possible. Planning for the transition to a live state has commenced with the expectation that all teams will be ready for a cut over to a live production state to be staggered across September October and November 2025
Q4 24-25 | Eastern Health | EH | 4000 | Advancing Cancer Services through Digital Chemotherapy Project | Health | Development and Integration | This project implements the EMR Oncology modules to all Eastern Health sites where Cancer Services are delivered providing electronic cancer medication prescription and management for more safe and timely care. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-01 | 2025-02-28 |  | 2025-02-28 | 0 | 511021 | 2025-03-31 |  | 2026-05-31 |  | 3438979 |  |  |  |  | Green | Green | Design phase in progress which includes design workshops scheduled through to end October 2025. Working groups in flight progressing well and triggering handover of configuration design for build.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 4002 | Mature Platform to Target State | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | The Mature Platform work has been defined to complete the implementation of the data pipelines and data objects in the EDH aligned to the approved target state architecture and transform and uplift operational processes aligned to new architecture. | Delivery | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 85310 |  | 2025-01-02 |  | 2025-12-31 |  | 1536799 |  |  |  |  | Green | Green | On track
Q4 24-25 | WorkSafe Victoria | WorkSafe | 4003 | Return to Work Product Pipeline Implementation | Employment, Skills and Workplace | Analyses and Statistics ,Business Intelligence,Data Management | Deployment of a production-grade Return to Work (RTW) Dashboard Product to business users including operational support processes user training and change management. As well as automated ingestion of Australian Bureau of Statistics data. | Delivery | Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-23 | 2024-10-31 |  | 2024-10-31 | 60290 |  | 2025-01-02 |  | 2025-12-31 | 2026-03-31 | 1318806 |  |  |  |  | Amber | Green | On track
Q4 24-25 | WorkSafe Victoria | WorkSafe | 4004 | Oracle Exadata Platform Refresh | Employment, Skills and Workplace | Systems Management | The project will upgrade the existing Oracle Exadata platform to improve/uplift Oracle Capacity and performance to meet current and future application landscape expansion. | Delivery | Cost Reduction (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-05 | 2024-11-29 |  | 2024-11-29 | 240072 |  | 2024-12-01 |  | 2025-10-27 |  | 2269561 |  |  |  | Green | Green | Green | On track
Q4 24-25 | Department of Health | DH | 4005 | Enterprise Operational Workforce Management System | Community Services | Human Capital / Workforce Management | Replace end-of-life Rostering, Time and Attendance systems for disability residential services, child protection, emergency response and maternal child health divisions across DFFH and DH to enhance workforce management and improve service delivery. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PRINCE2 | 2023-12-14 | 2024-09-30 |  | 2024-09-30 | 239974 |  | 2024-10-01 |  | 2026-06-30 |  | 3518876 |  |  |  | Green | Green | Green | Project is progressing to cost and schedule.
Q4 24-25 | Goulburn-Murray Rural Water Corporation | GMR Water | 4007 | Dartmouth - Telemetry Upgrade | Environment and Water | Systems Management | The project involves upgrading the industrial control system for Dartmouth Dam for increased reliability, replace aging components, integrate digital data recording and display and maintain essential manual controls | Closed - Completed | Efficiency/Productivity (Non Financial) | 2025-06-30 | PRINCE2 | 2021-07-14 | 2022-09-20 |  | 2022-09-20 | 204000 |  | 2023-09-15 |  | 2025-06-29 |  | 2030042 | 2549531 |  |  | Green | Green | Green | The project has been successfully implemented and formally closed, with all deliverables completed on schedule and in accordance with the defined scope and quality standards. Key milestones were achieved as planned, and any potential risks were effectively identified and managed throughout the project lifecycle. The outcomes have met stakeholder expectations, and all necessary documentation and handovers have been completed to ensure a smooth transition to ongoing operations or support.
Q4 24-25 | CenITex | CenITex | 4008 | AWS and Azure Cloud Landing Zone deployment | Government and Economy | Assets/Materials Management | This project iteratively implements Landing Zone feature enhancements. The focus is security enhancement standards implementation. Landing Zone “Official” security status implementation and delivery of a new cost model for efficient Cloud consumption | Delivery | Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2023-05-01 | 2023-06-30 |  | 2023-06-30 | 0 |  | 2023-07-01 |  | 2025-06-30 | 2026-06-30 | 1420000 | 1435951 |  |  | Green | Green | Green | Project is tracking to plan.
Q4 24-25 | CenITex | CenITex | 4009 | DC Exit Network Establishment – Phase 2 | Government and Economy | Assets/Materials Management | To establish a network extension from Burwood to Equinix ME2 using VicTrack colocation service at Equinix and then execute the base network infrastructure required at the data centre to start migrating Cenitex workloads out of Burwood to Equinix. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | PRINCE2 | 2024-11-01 | 2024-11-30 |  | 2024-11-30 | 0 |  | 2024-12-01 |  | 2025-10-30 |  | 1993326 | 2793326 |  |  | Green | Amber | Green | Project is tracking to plan.
Q4 24-25 | Goulburn Valley Region Water Corporation | GVR Water | 4011 | SCADA System Replacement | Environment and Water | Assets/Materials Management,Communication,Data Management,Systems Management | Replacement of the Supervisory Control and Data Acquisition (SCADA) System to ensure GVW's core operational monitoring and automation system remains fit for purpose and reduce business continuity risk. | Initiated |  |  | PMBoK | 2023-05-01 | 2025-04-30 | 2025-07-31 |  | 200000 | 415000 | [11 empty] | GVW has completed an initial engagement with a consultant who has outlined our concept design, validated our estimated cost and outlined a procurement approach involving 2 phases. The first phase of procurement is now complete. The second phase of procurement is underway.
Q4 24-25 | Hume Rural Health Alliance | HRHA | 4012 | Hume Regional EMR Preparation Project | Health | Customer Relationship Management,Records Management | The project will develop and deliver a series of business readiness activities prior to the full implementation of a whole of Hume Rural Health Alliance Electronic Medical Record (EMR), ensuring all IT environments are ready for the roll-out | Delivery | Increased Quality (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-13 | 2025-12-31 | 2025-03-31 | 2025-04-30 | 0 | 200000 | 2025-05-01 |  | 2026-06-30 |  | 4200000 | [5 empty] | Green | With initiation approved the project now moves into delivery developing a key set of artefacts to plan for the regional EMR implementation. A regional EMR is a high priority for the region to support the safety and quality of clinical care to attract and retain clinical workforce and to connect care to other health service providers and digital health initiatives
Q4 24-25 | Victorian Funds Management Corporation | VFMC | 4013 | Migration to cloud | Business and Industry | Systems Management | This project will transition our investment management system from an on-premises setup to a managed service offering, enhancing support, security and access to new functionality for our core technology platform. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-05-01 | 2024-05-28 |  | 2024-05-28 | 0 |  | 2024-12-01 |  | 2025-12-31 | 2026-03-31 | 2787000 |  |  |  | Green | Amber | Amber | Good progress has been made in setting up the environment and integration with third parties. However, the batch management migration is more extensive than anticipated and this will delay the planned go-live date. There is no direct financial impact for the delay.
Q4 24-25 | Transport Accident Commission | TAC | 4030 | Oracle Exadata Platform Refresh | Transport and Vehicles | Systems Management | The project will upgrade the existing Oracle Exadata platform to improve/uplift Oracle Capacity and performance to meet current and future application landscape expansion. | Delivery | Cost Reduction (Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-04 | 2024-11-29 |  | 2024-11-29 | 160048 |  | 2024-12-01 |  | 2025-10-27 |  | 1513041 |  |  |  | Green | Green | Green | On Track.
Q4 24-25 | Yarra Valley Water | YV Water | 4031 | Digital Metering – Customer Solutions | Environment and Water | Communication,Customer Initiated Assistance,Customer Preferences,Customer Relationship Management,Management of Process ,Reporting ,Visualisation | The project will deliver multi-channel communications and digital meter bill generation, thus providing Yarra Valley Water customers with timely communications, access to water usage information, and leak alerts, improving the end-to-end experience. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial) |  | Agile | 2023-09-01 | 2024-03-31 |  | 2024-03-31 | 650000 |  | 2024-04-01 |  | 2025-06-30 | 2025-08-31 | 2636860 |  |  |  | Amber | Green | Green | Project near completion with final testing underway
Q4 24-25 | South Gippsland Region Water Corporation | SGR Water | 4033 | ERP Replacement Program | Environment and Water | Assets/Materials Management,Financial Management,Systems Management | The project will migrate three ERP platforms (finance, assets, work management) to cloud to reduce legacy system and security risks, improving workforce efficiency at South Gippsland Water. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Increased Quality (Non Financial), Increased Revenue (Financial), Workforce Satisfaction (Non Financial) |  | Waterfall | 2024-03-21 | 2024-09-30 |  | 2024-09-30 | 600000 |  | 2024-10-01 |  | 2025-07-01 | 2025-08-29 | 7685000 |  |  |  | Green | Amber | Green | Project is currently being delivered to planned scope budget with a 6 day delay on go live to ensure testing was closed out. Hypercare period commences on 7 July 2025.
Q4 24-25 | State Electricity Commission (SEC) Victoria Pty Ltd | SECV | 4037 | Data and Analytics Platform | Energy and Resources | Analyses and Statistics ,Business Intelligence,Data Management | The platform will store data from SEC core systems and provide reporting and analytics capability to SEC business units to maximise value through data based decision making and data modelling. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-01-16 |  | 2025-01-20 | 240042 |  | 2025-01-20 |  | 2025-07-31 |  | 2734936 |  |  |  |  | Green | Green | Project is on Track with key functionality deployed into production and in use by the business. Project currently in Hypercare
Q4 24-25 | Alfred Health | ALFRED | 4038 | Alfred Health Monitoring Project (Philips) | Health | Systems Management | Alfred Health is enhancing Physiological Monitoring by upgrading the Philips Clinical Information System. The system will be consolidated across all care points, with Bedside, Telemetry, Transport Monitors, and Workstations upgraded or replaced. | Closed - Completed | Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Reputation (Non Financial), Workforce Satisfaction (Non Financial) | 2025-06-06 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-01 | 2024-11-01 |  | 2024-11-01 | 72429 |  | 2024-11-01 |  | 2025-06-06 |  | 4367571 |  |  |  |  | Green | Green | The Project is complete.
Q4 24-25 | State Revenue Office | SRO | 4045 | Revenue Management System - Foundation | Government and Economy | Development and Integration | The Revenue Management System (RMS) is the core backend software & technology managing tax-related activities for all customers. This initiative aims to establish the technical foundations to transition all revenue lines to utilise modern technology. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-03 | 2025-06-30 |  |  | 1411087 | [12 empty] | Planning activities are now complete, project will move to delivery in Q1 2025-26.
Q4 24-25 | Peninsula Health | PEN Health | 4046 | Patient Flow Management Solution | Health | Organisational Management | Electronic Patient Flow Management streamlines patient movement, enhances collaboration, optimises access and demand management, reduces length of stay, improves communication, and increases workplace satisfaction and providing bed visibility. | Delivery | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | PRINCE2 | 2023-09-08 | 2024-06-10 |  | 2024-08-07 | 50000 |  | 2024-12-20 |  | 2026-01-29 | 2026-04-30 | 2440404 |  |  |  |  | Green | Green | Functional stakeholder workshops are now completed; the Flow journey board requirements are defined. These requirements have now been consolidated and shared with hosting provider to explore integration ability and obtain a quote for the work so that required data can flow from Electronic Medical Record (EMR) into the Flow journey board.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 4047 | VicGrid Human Capital Management - System Establishment | Energy and Resources | Human Resources | The project will deliver the back-office system to manage VicGrid's workforce, enabling secure management of people's profiles, roles and responsibilities, in line with Whole of Victorian Government standards. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) | 2025-06-30 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-18 | 2024-12-17 |  | 2024-12-17 | 0 |  | 2025-02-03 |  | 2025-06-30 |  | 1200000 |  |  |  |  | Green | Green | The project has been successfully completed. It was delivered within the agreed scope, budget and schedule.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 4048 | VicGrid Finance & Procurement - System Establishment | Energy and Resources | Financial Management | The project will deliver the system to manage finances, budgets, and procurement processes for VicGrid, in line with VicGrid's requirements and in compliance with Whole of Victorian Government information security standards. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-18 | 2024-12-17 |  | 2024-12-17 | 0 |  | 2025-02-03 |  | 2025-06-30 | 2025-10-31 | 1490000 |  |  |  |  | Green | Green | The project is tracking well against scope budget and schedule.
Q4 24-25 | Victorian Legal Services Board & Commissioner | VLSBC | 4049 | Regulatory Management System | Law and Justice | Customer Relationship Management | A Regulatory Management System will be delivered. Replacement of legacy systems will improve delivery of service and modernisation of legal regulatory systems will support legal regulation in Victoria. | Postponed | Customer Satisfaction (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) | 2025-02-25 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-11-10 | 2023-08-22 |  | 2023-08-22 | 330680 |  | 2023-11-27 |  | 2026-05-01 |  | 18400000 |  |  |  |  | Red | Amber | The project delivery is currently postponed. The vendor completed a technical release and is no longer contracted to deliver the remaining scope. The business is now validating its requirements and assessing the feasibility with the remaining budget before engaging a vendor for any scope agreed to proceed. The delivery dates are subject to revision following the assessment.
Q4 24-25 | Liquor Control Victoria | LCV | 4050 | Liquor Control Victoria ICT relocation and support for hardware and software | Law and Justice | Systems Management | The project will relocate on-premises servers to Richmond, decommission legacy hardware, and improve software and hardware support to enable business continuity | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-04-01 | 2024-12-01 | 2025-03-31 | 2025-03-31 | 0 |  | 2025-06-27 |  | 2026-01-31 |  | 4373050 | [5 empty] | Green | The project is tracking well with the relocation of LCV's ICT hardware on track for completion in July 2025. Transition of the LCV systems and support will follow the completion of the hardware relocation.
Q4 24-25 | Liquor Control Victoria | LCV | 4051 | New liquor platform for Liquor Control Victoria (delivered by Service Victoria) | Law and Justice | Customer Initiated Assistance | The project will deliver online licence application forms and a digital proof of age card. Efficiency and data quality will be enhanced, resulting in an improved user experience. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-07-01 | 2022-07-01 |  | 2022-07-01 | 0 |  | 2022-10-01 | 2023-06-01 | 2026-06-30 |  | 4580000 | 6835000 |  |  |  | Green | Green | The online licence application forms went live on the Service Victoria portal in April 2025. The digital proof of age card is substantially built and on track for delivery within the schedule.
Q4 24-25 | South West Alliance of Rural Health | SWARH | 4052 | Windows Server Upgrades | Health | Assets/Materials Management | Upgrade of operating systems across SWARH Server environment​. This will provide enhanced performance and scalability of IT infrastructure and simplify management and streamline operations through modern tools and features. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2025-01-31 | 2025-02-01 |  | 2025-02-01 | 5000 |  | 2025-02-28 |  | 2026-12-20 |  | 2806000 |  |  |  |  | Green | Green | The project pilot phase has been successfully completed. The next phase is on schedule with the overall project tracking to Schedule and Budget
Q4 24-25 | South West Alliance of Rural Health | SWARH | 4053 | PACS Replacement | Health | Systems Management | Raplace the existing medial imaging Picture Archiving Communication System (PACS) used by Barwon Health Medical Imaging services. The current system is old and now unsupported with no capacity to upgrade to a new version. | Delivery | Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-09-01 | 2025-01-16 |  | 2025-01-16 | 5000 |  | 2025-02-01 |  | 2025-10-30 |  | 2295508 |  |  |  |  | Green | Green | The project remains on track and under budget. Server builds have been completed and handed over to the vendor for software installation and configuration.
Q4 24-25 | Department of Transport and Planning | DTP | 4054 | Energy Digital Transformation | Transport and Vehicles | Organisational Management | The Energy Digital Transformation project aims to enhance the Impact Assessment Unit’s digital capabilities to improve operational efficiency, customer engagement, and overall service delivery. | Delivery | Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-10 |  | 2025-09-30 |  | 1123594 | 1230577 |  |  |  | Green | Green | The project status is green and is tracking well against its scope, budget, and schedule.
Q4 24-25 | Department of Jobs, Skills, Industry and Regions | DJSIR | 4055 | TAFE Customer Relationship Management (CRM) tool phase 2 | Education | Customer Relationship Management | The Office of TAFE Coordination and Delivery and the TAFE Network work to improve student experiences and industry outcomes. This phase launches a modern CRM to streamline enrolments at two TAFEs and boost industry engagement across six. | Delivery | Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-17 | 2024-11-30 |  | 2025-02-19 | 1 |  | 2025-03-24 |  | 2025-11-30 |  | 4718530 |  |  |  |  | Green | Green | The project is tracking well against milestones. The Industry Engagement component of the project went live at six TAFEs as planned within budget, scope and timeline.
Q4 24-25 | Department of Transport and Planning | DTP | 4056 | Two-way radio | Transport and Vehicles | Communication | The project will leverage the state emergency radio network to implement two-way radio communication system, enabling enhanced safety of roadside operations through real-time location monitoring, duress alarm capability, and broader coverage. | Delivery | Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-01-01 | 2024-12-31 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2025-12-01 |  | 1507000 |  |  |  |  | Amber | Green | The project status is back to green. The project is tracking well against the project scope, budget, and schedule.
Q4 24-25 | Department of Transport and Planning | DTP | 4057 | OneView Separation | Transport and Vehicles | Systems Management | The project will migrate the Medical Review application to a dedicated instance of Dynamics 365 platform, addressing audit privacy concerns and ensuring stronger compliance with security standards and enhancing the protection of sensitive information | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-07-01 | 2024-09-24 |  | 2024-09-25 | 0 |  | 2024-10-01 |  | 2025-07-22 |  | 1092420 | 1264000 |  |  |  | Green | Amber | The project reported an amber status due to solution testing issues impacting the project schedule. The project team is working on mitigating these issues and will re-baseline the schedule to get the project status back on track.
Q4 24-25 | Department of Transport and Planning | DTP | 4058 | Transport Victoria website Release 2 and Release 3 | Transport and Vehicles | Development and Integration | The project will consolidate existing digital channels, delivering an enhanced customer experience that integrates all modes of transport, and enables longer term operational efficiencies by simplifying the underlying technical infrastructure. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-01 | 2025-01-06 |  | 2025-01-06 | 0 |  | 2025-01-13 |  | 2026-06-30 |  | 8119044 |  |  |  |  | Amber | Amber | The project status is amber due to development and testing-related issues impacting the project schedule and budget. The project team is working on mitigating these issues which are being monitored with the project control board.
Q4 24-25 | Department of Transport and Planning | DTP | 4059 | Pay Portal for Public Transport Ticketing (PTT) | Transport and Vehicles | Development and Integration | The project will roll out a digital pay portal, enabling commuters to interact with the new public transport ticketing (PTT) system, providing faster and easier ticketing transactions for Victorian commuters. | Delivery | Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-12-02 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2027-05-13 |  | 16700000 |  |  |  |  | Amber | Amber | The project is amber due to procurement-related issues impacting the project schedule. The project team is working closely with the other teams in the department and the steering committee to mitigate these issues.
Q4 24-25 | South West Alliance of Rural Health | SWARH | 4060 | Citrix environment upgrade | Health | Systems Management | Upgrade to the current Long Term Service Release (LTSR) of Citrix to improve platform performance and supportability. | Delivery | Efficiency/Productivity (Non Financial) |  | Waterfall | 2024-10-01 | 2024-10-30 |  | 2024-11-30 | 5000 |  | 2025-01-01 |  | 2025-05-31 | 2025-09-30 | 4467000 |  |  |  |  | Green | Green | Hardware and Citrix software upgrade have been completed. Device replacements have been completed at most sites. The project has been e-baselined to align the project to the existing Windows 11 upgrade project. The project is on track for completion by September 2025.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 4062 | Claims Systems Modernisation Initiative - Phase 1 | Employment, Skills and Workplace | Customer Relationship Management | The project will deliver a new claim management solution based on the already established CRM platform uplifting both usability & functionality to improve claims management. Phase 1 will roll out the functionality to WorkSafe's internal claims team. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-02-24 | 2025-02-24 |  | 2025-02-24 | 0 |  | 2025-02-25 |  | 2025-12-31 |  | 36083436 |  |  |  |  | Green | Amber | Re-baselining of release dates to be completed. Path to green involves a re-plan exercise and change request to approve revised schedule.
Q4 24-25 | South East Water | SE Water | 4064 | Asset Management Platform Uplift | Environment and Water | Assets/Materials Management | Upgrade of SEW's Asset Management system from on-premise to cloud including major version uplift. | Delivery | Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-07-01 | 2025-03-15 |  | 2025-03-15 | 0 |  | 2025-03-17 |  | 2025-12-19 |  | 1305000 |  |  |  |  | Green | Amber | Project is progressing with development environment build complete. Reporting AMBER due to resourcing constraints as well as uncertainty around the scope of components of the required integrations.
Q4 24-25 | South East Water | SE Water | 4065 | Enterprise Telephony Uplift | Environment and Water | Communication | Replacement and uplift of SEW's enterprise telephony solution across the organisation. | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2025-01-06 | 2025-02-28 |  | 2025-03-03 | 0 |  | 2025-03-03 |  | 2025-11-30 |  | 1220000 |  |  |  |  | Green | Green | Phase 1 of the new telephony solution rolled out to 3 priority areas of the organisation. Decommissioning of physical phones has been completed and project remains on track to roll out remainder of the solution across Q1-Q2 in FY26.
Q4 24-25 | CenITex | CenITex | 4066 | Software Defined Datacentre (SDDC) Migration | Government and Economy | Assets/Materials Management | To design configure and consume an alternate VMWare based Private Cloud platform, and migrate Cenitex and customer applications from the current platform to the Multicloud solutions including a new IaaS Platform with built-in backup capability. | Delivery | Cost Avoidance (Financial), Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Revenue (Financial) |  | PRINCE2 | 2025-02-21 | 2025-04-01 | 2025-02-27 | 2025-02-27 | 0 |  | 2025-11-30 | 2025-03-10 | 2025-11-30 |  | 1431025 |  |  |  |  | Green | Green | Project is tracking to plan.
Q4 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 4069 | High Performance Compute and Storage infrastructure refresh and upgrade (HPC) | Health | Assets/Materials Management,Systems Management | The project will deliver a refreshed and upgraded High Performance Compute (HPC) and Storage infrastructure for Peter Mac Research, replacing outdated hardware with advanced, high-performance equipment. | Initiated |  |  | PRINCE2 | 2024-10-01 | 2025-11-28 |  |  | 0 | [12 empty] | Business case in progress to seek funding approval
Q4 24-25 | Peter MacCallum Cancer Centre | Peter MAC | 4070 | Network Infrastructure Refresh | Health | Assets/Materials Management,Systems Management | The project will deliver a comprehensive refresh of Peter Mac's network infrastructure, including all physical components and the provision of layer 2 and layer 3 services across the WAN, LAN, and WLAN. | Initiated |  |  | PRINCE2 | 2024-10-01 | 2025-10-31 | 2025-11-30 |  | 0 | [12 empty] | Business case in progress to seek funding approval
Q4 24-25 | State Revenue Office | SRO | 4071 | Inbound Correspondence | Government and Economy | Development and Integration | This Project focuses on inbound communication – phone calls, forms, and emails initially. It aims to enhance data quality, streamline processes, and improve communication channels to deliver a seamless customer experience and boost staff productivity | Initiated |  |  | Agile | 2025-02-01 | 2025-06-30 |  |  | 637738 | [12 empty] | Planning activities are now complete, project will move to delivery in Q1.
Q4 24-25 | State Revenue Office | SRO | 4072 | Enabling Technology | Government and Economy | Development and Integration | This project is establishing enabling technologies and processes to enhance security and uplifting capabilities for future project delivery. | Initiated |  |  | Agile | 2025-02-01 | 2025-06-30 |  |  | 271913 | [12 empty] | Planning activities are now complete, project will move to delivery in Q1.
Q4 24-25 | Western Health | WH | 4073 | Network Switches Asset Replacement 23/24 | Health | Development and Integration | End of life replacement of network switches at Sunshine Hospital to ensure network reliability, supportability and security, enabling WH to deliver services for the future, high quality connected care and better health outcomes for our community. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2024-01-02 | 2024-02-23 |  | 2024-02-26 | 0 |  | 2024-11-18 |  | 2025-08-26 | 2025-10-13 | 4156643 |  |  |  |  | Green | Green | Phase 2 of 3 to be completed by 29 August 2025 in accordance with plan. Phase 3 and overall project will be completed by 13 October 2025
Q4 24-25 | Grampians Rural Health Alliance | GRHA | 4074 | Grampians Health Success Factors Phase 3 | Health | Human Resources | The regional adoption of the full Grampians Health instance of SAP Success Factors by GRHA Health Services (Core HR, Recruitment, Onboarding, Payroll, Performance & Goals and Integration Centre). | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-05-05 | 2025-10-31 |  |  | 78000 | [12 empty] | Phase 3 initiation commenced, scoping for the GRHA implementation continues with a target to commence procurement activities in Q1.
Q4 24-25 | Melbourne Water | MELB Water | 4075 | Data Protection Initiatives | Environment and Water | Data Management | Prepare and execute the tender for a Secure Access Service Edge (SASE) product selection. Identify and deploy a Data Loss Protection (DLP) Capability for Melbourne Water | Initiated |  |  | PMBoK | 2024-07-26 | 2025-05-15 |  |  | 0 | [12 empty] | As at 20250630: Business Case pending approval, anticipated the project budget will be under $1M and not not eligible for reporting. Update to be provided next quarter.
Q4 24-25 | Melbourne Water | MELB Water | 4076 | Mobile Device Management | Environment and Water | Assets/Materials Management | Enhance support for flexible remote working arrangements for staff improving management of corporate devices by implementing a system that effectively addresses the challenges of remote device management and supports Bring your own device policies. | Initiated |  |  | PMBoK | 2024-08-21 | 2025-05-21 | 2025-09-12 |  | 0 | [12 empty] | As at 20250630: Tender assessment progressing to inform the Business Case for submission.
Q4 24-25 | Department of Education | DE | 4078 | Academy Customer Relationship Management_Course Management | Education | Customer Relationship Management,Data Management,Reporting | The project will improve business processes focusing on the Victorian Academy of Teaching and Leadership’s relationship management and enables the effective marketing management delivery and reporting of professional learning to Victorian educators. | Delivery | Efficiency/Productivity (Non Financial), Workforce Satisfaction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-03-01 | 2024-08-16 |  | 2024-08-30 | 0 |  | 2025-01-28 |  | 2026-08-13 |  | 9649702 |  |  |  |  | Green | Green | Project is on-track, within budget and meeting scheduled milestones. Risks are being effectively managed.
Q4 24-25 | Department of Education | DE | 4079 | Student Insight Platform Establishment and Digital Enrolment Product – Phase 2 | Education | Customer Relationship Management | The project builds on the products delivered in previous phase of the Student Insight project by maintaining the operations and migrating functions and data to the Education Cloud. | Closed - Completed | Cost Reduction (Financial), Customer Satisfaction (Non Financial), Increased Quality (Non Financial) | 2025-06-30 | Agile | 2024-11-01 | 2025-01-15 |  | 2025-01-29 | 0 |  | 2025-02-01 |  | 2025-06-30 |  | 3400000 |  |  |  |  | Green | Green | The project has successfully delivered the scope of this phase of the project and is now closed.
Q4 24-25 | Yarra Valley Water | YV Water | 4080 | IT Systems Monitoring & Logging | Environment and Water | Security Management ,Systems Management,Visualisation | Implement a platform which will encompass comprehensive monitoring, logging, synthetic monitoring, and a unified monitoring dashboard to enhance security, improve reliability, and visibility into our IT infrastructure and application performance. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-02 | 2025-01-31 |  | 2025-02-04 | 48000 |  | 2025-02-04 |  | 2027-02-28 |  | 1334300 |  |  |  |  | Green | Green | Project delivered Pilot and a Non-Production environment inline to agreed System Architecture and Design. Production environment build has commenced
Q4 24-25 | Department of Education | DE | 4081 | Service Tracking and Reporting Legacy (STaR) | Education | Communication,Data Management,Forms Management,Reporting ,Tracking and Workflow | The solution will uplift user experience for staff through better controls, efficient case management, robust data visualisations and reporting. Providing actionable insights to influence operational or policy changes for better student outcomes. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-09-01 | 2024-10-31 |  | 2024-11-20 | 0 |  | 2024-12-01 |  | 2025-06-30 | 2025-12-31 | 3000000 |  |  |  |  | Amber | Amber | The project has been delayed due to issues with change management resourcing, the project now expects to complete in Q2 FY26
Q4 24-25 | Department of Education | DE | 4082 | Student Support and Intervention | Education | Analyses and Statistics ,Customer Relationship Management,Data Management,Records Management ,Routing and Scheduling,Tracking and Workflow | This solution streamlines service referrals and case management. Increasing compliance with privacy information security record keeping and other legal obligations ensuring compliance to the departments legislative and regulatory responsibilities. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-10-01 | 2024-12-10 |  | 2025-01-10 | 0 |  | 2025-02-19 |  | 2025-06-30 | 2025-12-31 | 3651000 |  |  |  |  | Amber | Amber | Business rollout is scheduled for term Q1 FY26 following the resolution of the change management resource issue and subsequent re-baselining. Integration and legacy data retention risks have been identified. Analysis is underway to determine any impact on the delivery timeline. The project plans to roll out the core functionality of the system in Q1FY26
Q4 24-25 | Victorian Fisheries Authority | VFA | 4088 | Licensing Quota Management System | Business and Industry | Customer Initiated Assistance,Data Management,Management of Process ,Reporting ,Systems Management | The project will digitise the commercial quota management, licencing and permit application process, by delivering a self-service mobile application for commercial fishers and permit holders, improving access to data and support from VFA. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial), Customer Satisfaction (Non Financial), Efficiency/Productivity (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2022-06-01 | 2022-11-14 |  | 2024-07-14 | 0 |  | 2025-01-14 |  | 2026-06-30 |  | 1450000 |  |  |  |  | Green | Green | The project is tracking well against milestones
Q4 24-25 | Social Services Regulator | SSR | 4089 | Social Services Regulator Regulation Management System | Community Services | Customer Relationship Management,Records Management | Deliver a regulatory management system to enable social services providers to apply for registration with the Social Services Regulator (SSR) to enable improved monitoring and enforcing of social services standards per the Social Services Act 2021. | Closed - Completed | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) | 2025-04-17 | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-08-18 | 2023-09-04 |  | 2023-09-04 | 0 |  | 2023-09-04 |  | 2025-04-17 |  | 1213171 |  |  |  |  | Green | Green | Project completed to cost and schedule on its intended scope and output. To support expanding regulatory responsibilities, the SSR has implemented a Regulatory Management System (RMS) solution, reducing the need for manual processes whilst also providing greater visibility of regulatory activities and enabling reporting capabilities. The Regulator delivered on the commitment of reducing administrative burden by introducing an online authenticated registration portal, which enables Providers to register online and SSR registration staff to accept and process registration applications efficiently and securely.
Q4 24-25 | Victorian Rail Track | VicTrack | 4090 | Cyber Security Roadmap | Transport and Vehicles | Security Management | To uplift the cyber-security maturity of VicTrack, fulfil our regulatory obligations under VPDSS and the Essential 8, and secure critical assets against cyber threats. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-31 | 2025-03-19 |  | 2025-03-19 | 0 |  | 2025-03-19 |  | 2028-06-30 |  | 12530000 | [5 empty] | Amber | The project reported Amber due to a slow start with resource recruitment, and capacity constraints to complete requirements necessary for the multiple concurrent procurement activities. This has delayed the delivery of some Year 1 milestones. The program has received approval from the steering committee to re-baseline the project schedule and is currently completing this. It’s expected this re-baselining will bring the project back to Green for the July 2025 steering committee and the project will continue to monitor progress against this re-baselined schedule.
Q4 24-25 | Victorian Rail Track | VicTrack | 4091 | Project Backup Server & Storage Replacement | Transport and Vehicles | Data Management | Refresh of the current storage and backup solution to improve storage capacity, introduce additional security features, uplift to provide better resilience against modern cyber-attacks. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-01-06 | 2025-06-27 |  | 2025-06-27 | 0 |  | 2025-06-27 |  | 2026-06-30 |  | 1594439 | [5 empty] | Amber | Key resource time allocation to this project has been impacted timelines, causing a 2-3 week delay.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 4094 | Payroll Technical Upgrade Project | Environment and Water | Human Resources | The project involves the technical upgrade of DEECA's SAP Payroll solution, as the current license and version support are due to expire by the end of 2025. Upgrading to SAP H4S4 is a mandatory requirement to ensure payroll business continuity. | Delivery | Compliance (Non Financial), Risk Reduction (Non Financial) |  | Waterfall | 2024-11-04 | 2024-12-24 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2025-12-19 |  | 3750000 | [5 empty] | Green | The project is tracking well against scope budget and schedule. Detailed design has been completed and the build phase is progressing well in preparation for the commencement of testing.
Q4 24-25 | Victorian Public Sector Commission | VPSC | 4102 | Cloud Migration and Transformation | Government and Economy | Analyses and Statistics | Modernising VPSC’s analytics by migrating to a secure cloud platform using Microsoft Fabric, Power Platform, and Entra ID to streamline reporting, improve data quality, and enable scalable, AI-driven workforce insights. | Delivery | Cost Avoidance (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-08-29 | 2024-12-19 |  | 2024-12-19 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1773267 | [5 empty] | Green | The VPSC Cloud Transformation project is on track having secured project funding completed an assurance audit and commenced the build phase following a successful procurement process. The project is focused on building the core system preparing for data migration and engaging users to ensure the solution meets future needs.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 4103 | Common Technology Platform (CTP) Program - Phase 3 | Government and Economy | Security Management | The CTP Program was established to deliver the technology strategy via a 3-year phased approach. Phase 3 will uplift the 2 remaining platforms (spatial and digital) and enhance platforms established during previous phases. | Delivery | Cost Reduction (Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-03 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2026-06-30 |  | 1798000 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q4 24-25 | Department of Energy, Environment and Climate Action | DEECA | 4104 | Cyber Security Uplift Program | Government and Economy | Security Management | Cyber Security program will deliver a set of controls, processes and education that aligns with the Victorian Cyber Security Strategy and leverages the WoVG capabilities to reduce and address cyber security risks. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-02-01 | 2024-12-12 |  | 2025-03-21 | 0 |  | 2025-03-21 |  | 2027-06-30 |  | 6034000 | [5 empty] | Green | The project is tracking well against scope, budget and schedule.
Q4 24-25 | Hume Rural Health Alliance | HRHA | 4106 | Cyber Security Maturity Uplift implementation | Health | Security Management | The purpose of this project is to ensure a regional uplift in Cybersecurity through reducing risks uplifting governance and risk management practices and alignment to the Department of Health's Cyber Security Assurance Framework. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2023-10-02 | 2024-02-12 |  | 2024-02-12 | 0 |  | 2024-07-01 |  | 2027-06-30 |  | 1950000 | [5 empty] | Green | Project activities remain on track.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 4107 | Claims Management System Uplift for Workplace Injury and Rehabilitation Compensation (WIRC) Act Amendment Bill | Employment, Skills and Workplace | Systems Management | This project will operationalise the proposed WIRC Act Amendment Bill and uplift existing claims management systems to ensure high-quality service and improve support to users of Victoria’s workers compensation scheme. | Delivery | Compliance (Non Financial), Increased Quality (Non Financial), Social Improvement (Non Financial) |  | Waterfall | 2024-11-25 | 2025-03-05 |  | 2025-03-05 | 0 |  | 2025-03-05 |  | 2026-12-15 |  | 1728437 | [5 empty] | Amber | Status is Amber due to a scheduling risk associated with the passage of the Bill through Parliament.
Q4 24-25 | South East Water | SE Water | 4108 | Service Management System Implementation | Environment and Water | Systems Management | Replacement and transformation of SEW's internal Service Management solution used across multiple business functions. This project will deliver uplift in internal capabilities and deliver efficiencies through streamlining service management processes | Delivery | Cost Reduction (Financial), Increased Quality (Non Financial) |  | Waterfall | 2024-10-01 | 2025-03-28 |  | 2025-04-01 | 0 |  | 2025-04-01 |  | 2026-01-30 |  | 1380500 | [5 empty] | Green | Project tracking well overall. Minor delays to schedule due to some delays in discovery and planning. Vendor to compress build schedule to ensure project timeframes can be upheld.
Q4 24-25 | South East Water | SE Water | 4109 | Payment Gateway Replacement | Environment and Water | Financial Management | Replacing current payment gateway solution which is end of life. Project will move all existing payment channels for customers across to a new provider. | Delivery | Customer Satisfaction (Non Financial), Risk Reduction (Non Financial) |  | Agile | 2024-06-01 | 2025-02-28 |  | 2025-03-10 | 0 |  | 2025-04-01 |  | 2025-11-30 |  | 2120000 | [5 empty] | Amber | Project reporting AMBER due to the risks associated if the project doesn't deliver on schedule. Overall, the project is tracking well with 80% of components delivered and tested. Project will commence end-to-end integration testing in August and planning for go-live in September.
Q4 24-25 | WorkSafe Victoria | WorkSafe | 4111 | Cheques Migration Strategy | Employment, Skills and Workplace | Financial Management | This project will operationalise the Victorian Government directive to cease cheque payments and will implement complex system changes to ensure faster payments for injured workers and providers and reduce administration costs. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2024-10-08 | 2025-05-27 |  | 2025-05-28 | 0 |  | 2025-05-28 |  | 2027-12-31 |  | 2143701 | [5 empty] | Green | On track
Q4 24-25 | Department of Transport and Planning | DTP | 4112 | Records Management Uplift - Stage 2b | Transport and Vehicles | Records Management | The project will review and refine the records management environment and consolidate organisational data into Records365, standardising and uplifting the records management solution & practices across the DTP. | Initiated |  |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-07 | 2025-07-10 |  |  | 0 | [12 empty] | The project planning is on track, and initiation activities are ongoing.
Q4 24-25 | Melbourne Water | MELB Water | 4117 | Data Lake | Environment and Water | Data Management | Build a data warehouse solution that is scalable, secure and evolves to meet growing business insights and reporting needs of Melbourne Water. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | PMBoK | 2024-02-01 | 2024-04-02 |  | 2024-04-02 | 0 |  | 2024-04-02 |  | 2026-05-15 |  | 3301197 | [5 empty] | Amber | As at 20250630: Project is Amber due to risks with data complexity. As a result, may require additional analysis of existing data sets prior to migration to ensure all functionality is retained.
Q4 24-25 | CenITex | CenITex | 4118 | Cenitex Office Relocation | Government and Economy | Assets/Materials Management | Make 35C fit for Cenitex purpose to undertake its core role in providing support and technology solutions for customers across WoVG. With a lease end of Jun’25 at 80C, the timeline to undertake this work is tight with a early June relocation target. | Delivery | Cost Reduction (Financial), Customer Satisfaction (Non Financial) |  | PRINCE2 | 2025-03-20 | 2025-03-20 |  | 2025-03-20 | 0 |  | 2025-03-20 |  | 2025-10-31 |  | 2570677 | [5 empty] | Green | Project is tracking to plan.
Q4 24-25 | Victorian Rail Track | VicTrack | 4120 | HCI Replacement Project | Transport and Vehicles | Systems Management | Hyper-converged infrastructure (HCI) utilises physical servers to create a software-defined IT environment that virtualises all components of traditional hardware-based systems. | Delivery | Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2025-04-01 | 2025-05-16 |  | 2025-05-16 | 0 |  | 2025-05-16 |  | 2026-12-31 |  | 9000000 | [5 empty] | Green | Project is tracking well
Q4 24-25 | Department of Families, Fairness and Housing | DFFH | 4121 | Replacement Document and Records Management System | Community Services | Records Management | Replace the existing out-of-support records management system (Housing TRIM) with a new, supported record keeping system that uses cloud storage and provides staff with improved business functionality. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Risk Reduction (Non Financial) |  | Hybrid - PRINCE2 and Agile (incl PRINCE2 Agile method) | 2024-11-29 | 2025-04-09 |  | 2025-04-09 | 351860 |  | 2025-04-09 |  | 2026-03-31 |  | 5898928 | [5 empty] | Amber | Project is progressing but is Amber primarily due to constraints in accessing required services. Impact to schedule is currently being assessed.
Q4 24-25 | Melbourne Water | MELB Water | 4127 | Asset Maintenance application upgrade | Environment and Water | Tracking and Workflow | Upgrade of our asset management system to a modern platform that enhances scalability, security, and usability. Ensuring ongoing support beyond 2025, reduces operational risk, and provides advanced features and improved reporting. | Initiated |  |  | Waterfall | 2023-10-09 | 2026-04-09 |  |  | 0 | [12 empty] | As at 20250630: Features Review process is progressing well, the team continues meeting with key stakeholders and holding workshops. Business Case is being drafted.
Q4 24-25 | Melbourne Water | MELB Water | 4128 | SCADA For Our Future | Environment and Water | Assets/Materials Management | A next-generation system to enhance real-time monitoring, decision-making, and automation across our water, sewerage, & drainage networks. Providing advance alarm and incident management to meet growing service complexity and performance expectations | Initiated |  |  | Waterfall | 2019-10-25 | 2025-11-25 |  |  | 0 | [12 empty] | Preferred supplier has been selected and approved by the Managing Director and design workshops held in February and March. Project will go through an additional stage gate (PBC) as part of Melbourne Waters project governance before proceeding to full Business Case sign off expected before the end of 2025.
Q4 24-25 | Melbourne Water | MELB Water | 4129 | Dam Surveillance Information System | Environment and Water | Management of Process | Replacement of an outdated system with a modern, fully supported solution that brings enhanced automation, smarter features, and improved reporting—empowering the Water Control teams to work more efficiently and make better-informed decisions | Delivery | Risk Reduction (Non Financial) |  | Agile | 2023-05-10 | 2024-12-10 |  | 2024-12-10 | 0 |  | 2024-12-10 |  | 2026-10-05 |  | 3340950 | [5 empty] | Amber | As at 20250630: Amber status due to solutioning issues impacting contract establishment and resourcing constraints.
Q4 24-25 | Treasury Corporation of Victoria | TCV | 4130 | Infrastructure IT Refresh | Government and Economy | Systems Management | Deployment of a resilient IT infrastructure with cloud-based disaster recovery and secure remote access. It will enhance system uptime, disaster recovery speed and secure remote work capabilities whilst ensuring continuity of TCV’s critical systems. | Delivery | Compliance (Non Financial), Cost Avoidance (Financial) |  | Waterfall | 2025-04-01 | 2025-04-22 |  | 2025-04-22 |  |  | 2025-06-20 |  | 2025-11-30 |  | 1476000 | 1536000 |  |  |  |  | Green | Project on track
Q4 24-25 | Western Health | WH | 4132 | Workstation on Wheels (WoW) replacement | Health | Systems Management | This project will replace end-of-life hardware for Workstations on Wheels (WoW) with updated hardware and software, enabling patient record access and update for doctors and nurses to provide quality patient care. | Delivery | Efficiency/Productivity (Non Financial) |  | PRINCE2 | 2025-02-24 | 2025-06-05 |  | 2025-06-06 | 0 |  | 2025-06-23 |  | 2025-11-28 |  | 2400000 | [5 empty] | Green | All items to be replaced have been identified. Currently awaiting confirmation of new equipment delivery dates from the vendor
Q4 24-25 | Holmesglen Institute of TAFE | Holmesglen TAFE | 4135 | ICT Infrastructure (Servers, LAN, Wifi, Telephony) & Data Centre Refresh | Employment, Skills and Workplace | Systems Management | The project will replace and upgrade the end-of-life ICT infrastructure and data centre with enhanced cyber security protection, minimising security risks and enabling faster, advanced technology access for students and staff at Holmesglen. | Initiated |  |  | Waterfall | 2025-03-26 | 2025-07-28 |  |  | 0 | [12 empty] | The Asset and Infrastructure Committee endorsed the development of a business case for the ICT infrastructure refresh, including a market engagement process to inform the proposal. A formal tender process was successfully conducted to gather detailed solution and costing information. Based on the findings, the business case was developed and subsequently endorsed by the Holmesglen Board. The project is now ready to proceed to the next phase of implementation planning and procurement.
Q4 24-25 | Western Health | WH | 4136 | Automatic Dispensing Cabinets (ADC) | Health | Systems Management | Implementation of automated medication cabinets replacing manual shelving for electronically tracked & secure storage of Imprest medications, enabling timely & safe medication access for staff at new Footscray Hospital delivering quality patient care | Delivery | Risk Reduction (Non Financial) |  | PRINCE2 | 2019-05-14 | 2019-09-04 |  | 2020-01-06 | 0 |  | 2024-03-04 |  | 2026-06-28 |  | 2502072 | [5 empty] | Green | Project is on track
Q4 24-25 | Southern Metropolitan Cemeteries Trust | SMCT | 4137 | PeoplePro (Human Resources Information System) | Health | Human Capital / Workforce Management ,Human Resources | SMCT's current human resources system is no longer vendor-supported. A replacement system will provide greater efficiencies, employee experience, decision-making and information through more seamless data management and improved processes. | Delivery | Compliance (Non Financial), Efficiency/Productivity (Non Financial), Increased Quality (Non Financial), Workforce Satisfaction (Non Financial) |  | Waterfall Agile hybrid | 2022-07-28 | 2024-10-22 |  | 2024-10-22 | 311733 |  | 2024-11-18 |  | 2027-06-30 |  | 1932705 | [5 empty] | Amber | The project status is AMBER due to a need to resolve a functional integration issue affecting business processes and reporting. The mitigation is to assess the viability of a third-party solution while working with the vendor and implementation partner to resolve the issue.